## All
ID | Title | Functional/Tech Spec | Regression? | Automation | UFT Script | Target to Complete | Target Completion (UFT Script code) | Assigned To | Status (UFT script) | Hours needed | Need Clarification | Comments
1 | 01-Div Part - Author tries to edit a Division Part at PreProduction Status to Change the Part Description | 1 - DivisionalPartRequest | N
2 | 01-Div Part Author tries to edits a Division Part at Production Status to Change the Part Description | 1 - DivisionalPartRequest | N
6 | 18-VM-Cut Dataset - Part related to ECN | 18 - VendorManagement
7 | 18-VM-Cut Dataset - Part Related to Deviation | 18 - VendorManagement
13 | 18-CPR-Classify a Part-Div Part created in UA | 2 - CommercialPartRequest
17 | 04-CAE - Admin needs to change part data for a down rev'd part | 4 - DisciplineSpecificEdit | Y |  |  |  | April 30
18 | 04-CAE - Admin needs to change part data for a Released Part to Lift Eng Control Flag | 4 - DisciplineSpecificEdit | Y | High (10) |  |  | April 30
19 | 04-CAE - Admin needs to change part data for an Electro-Mech Part that is related to an ECN | 4 - DisciplineSpecificEdit | Y | High (10) |  |  | April 30
20 | 04-DFM - Someone in the DFM Group needs to change Part data for a down rev'd Part | 4 - DisciplineSpecificEdit | N
21 | 04-DFM Group Member needs to change Part data for a Part that is related to an ECN | 4 - DisciplineSpecificEdit | N
22 | 04-DFM Group Member needs to change Part data for a Released Commercial Part | 4 - DisciplineSpecificEdit | Y |  |  |  | April 30
23 | 04-DFM Group member needs to change Part data for a Released Divisional Part | 4 - DisciplineSpecificEdit | Y |  |  |  | April 30
24 | 04-DSE- A Safety Group member needs to Change Part data for a down rev'd Part | 4 - DisciplineSpecificEdit | Y |  |  |  | April 30
25 | 04-DSE- Safety Group member needs to Change Part data for a Part that is related to an ECN | 4 - DisciplineSpecificEdit | N
26 | 04-DSE- Safety Group member needs to Change Part data for a Released Part | 4 - DisciplineSpecificEdit | Y |  |  |  | April 30
27 | 04-DSE- SBM Engineer needs to Change Part data for a Part that is related to an ECN | 4 - DisciplineSpecificEdit | N | High (10)
28 | 04-DSE- SBM Engineer needs to Change Part data for a Released Part | 4 - DisciplineSpecificEdit | N | High (10)
29 | 04-DSE- An SBM Engineer needs to Change Part data for a down rev'd Part | 4 - DisciplineSpecificEdit | N
30 | 04-DSE- A member of the Compliance Edits group needs to add-change ECCN and or HTS Codes for a Released Part | 4 - DisciplineSpecificEdit | Y | High (10) |  |  | April 30
31 | 04-DSE- Trade Compliance member needs to make a change to a down rev'd part | 4 - DisciplineSpecificEdit | N
32 | 04-DSE- Trade Compliance member needs to add-change ECCN and or HTS Codes for a Part that is related to an ECN | 4 - DisciplineSpecificEdit | Y | High (10) |  |  | April 30
37 | 17-SR- Rate a Vendor | 17 - SupplierRating | Y | Low (2) |  |  | April 30
38 | 18-VM-Vendor Part Creation-Commodity Support Engineer | 18 - VendorManagement | Y |  |  |  | April 30
40 | 18-VM-Vendor Part Creation-Using migrated Div Part and Vendor | 18 - VendorManagement
41 | 18-VM-Vendor Part Creation-Past Revision of Div Part | 18 - VendorManagement
42 | 18-VM-Vendor Part Creation-Duplicate Vendor Part | 18 - VendorManagement |  | Medium (5)
47 | 18-VM-Vendor Part Modify-Validate property setup and style sheets | 18 - VendorManagement |  | Low (2)
51 | 18-VM-Vendor Part Modify-Div Part not latest revision | 18 - VendorManagement
53 | 21-Edit a Project Form that is releated to an open ECN | 21 - AdminEditor | Y |  |  |  | February 28 | Rodji | DONE
54 | 01-Div Part- Planner Assigns a new Oracle Org to exisiting Assembly Part | 1 - DivisionalPartRequest | Y | High (10) | Complete |  | January 31 | Marjorie | DONE |  | YES | Test case is similar to Test case ID 449
55 | 18-VM-Copy and Paste Dataset to Part- Div part released to comm eng role | 18 - VendorManagement |  | Low (2)
56 | 04-CAE - Admin needs to change part data for a Released PCBA Part | 4 - DisciplineSpecificEdit | Y | High (10) |  |  | April 30
66 | 6-Create a Release ECN to change a Parts item status from Proto to Prod-Test 7.xlsx | 6 - ReleaseECN | N
67 | 6-Create a Release ECN to change a Parts item status from Proto to Prod-Test 8.xlsx | 6 - ReleaseECN | N
68 | 6-Create a Release ECN to change a Parts item status from Proto to Prod-Test 9.xlsx | 6 - ReleaseECN | Y |  | WIP | January 19 | January 31 | Rodji | DONE
69 | 6-Create a Release ECN to change a Parts item status from Proto to Prod-Test 10.xlsx | 6 - ReleaseECN | Y |  |  |  | January 31 | Rodji | DONE
70 | 6-WF - Create a Release ECN to change a Parts item status from Proto to Prod-Test 1.xlsx | 6 - ReleaseECN | Y | High (10) |  | January 27 | January 31 | Rodji | DONE
71 | 02-CPR-Commercial Part Modify-migrated comm part | 2 - CommercialPartRequest
72 | 02-CPR-Commercial Part Modify-Comm Part related to Open ECN | 2 - CommercialPartRequest |  | Low (2)
73 | 02-CPR-Commercial Part Modify-Comm Part in assembly of Open ECN | 2 - CommercialPartRequest
76 | 5-CHG-Add a File to Released ECN-Test 1.xlsx | 5 - ChangeECN | Y |  |  |  | February 28 | Rodji | IN PROGRESS |  | YES | 1) Test Case 1 is all about adding a file to a released ECN however on Step 4 it stated to delete a file. Deletion of file(s) from released ECN is already covered in Test Case 2 2) Can't execute this test script manually by adding a file to a released ECN with user having an Author Access. It will throw an error upon adding a file to a released ECN under Files folder
77 | 5-CHG-Add a Reviewer to an ECN-Test 1.xlsx | 5 - ChangeECN | Y |  |  |  | February 28 | Rodji | DONE
78 | 5-CHG-Assign Effectivity Date-Test 1.xlsx | 5 - ChangeECN | Y | Medium (5) |  |  | February 28 | Rodji | DONE
79 | 5-CHG-Assign Effectivity Date-Test 2.xlsx | 5 - ChangeECN | Y |  |  |  | February 28 | Rodji | DONE
80 | 5-CHG-Assign Effectivity Date-Test 3.xlsx | 5 - ChangeECN | N
81 | 5-CHG-Assign Effectivity Date-Test 4.xlsx | 5 - ChangeECN | N
82 | 5-CHG-Assign Effectivity Date-Test 5.xlsx | 5 - ChangeECN | Y |  |  |  | February 28 | Rodji | DONE
83 | 5-CHG-Assign Effectivity Date-Test 6.xlsx | 5 - ChangeECN | Y |  |  |  | February 28 | Rodji | DONE
84 | 5-CHG-Assign Effectivity Date-Test 7.xlsx | 5 - ChangeECN | Y |  |  |  | February 28 | Rodji | DONE
85 | 5-CHG-Assign Effectivity Date-Test 8.xlsx | 5 - ChangeECN | Y |  |  |  | February 28 | Rodji | DONE
86 | 5-CHG-Check Status of ECN-Test 1.xlsx | 5 - ChangeECN | N
87 | 5-CHG-Check Status of ECN-Test 2.xlsx | 5 - ChangeECN | N
88 | 5-CHG-Std ECN Add Additional Reviewer-Test 1.xlsx | 5 - ChangeECN | Y |  |  |  | February 28 | Rodji | DONE
89 | 5-CHG-Std ECN Cancellation-Test 1.xlsx | 5 - ChangeECN | Y |  |  |  | February 28 | Rodji | DONE
90 | 5-CHG-Std ECN Cancellation-Test 2.xlsx | 5 - ChangeECN | Y |  |  |  | February 28 | Rodji | DONE
91 | 5-CHG-Std ECN Design Doc work Needed-Test 1.xlsx | 5 - ChangeECN | Y |  |  |  | February 28 | Rodji | DONE
92 | 5-CHG-Std ECN Design Doc work Needed-Test 2.xlsx | 5 - ChangeECN | Y |  |  |  | February 28 | Rodji | DONE
93 | 5-CHG-Std ECN Expedite Approve or Reject-Test 1.xlsx | 5 - ChangeECN | Y |  |  |  | February 28 | Rodji | DONE | 5
94 | 5-CHG-Std ECN Expedite Approve or Reject-Test 2.xlsx | 5 - ChangeECN | N
95 | 5-CHG-Std ECN Expedite Approve or Reject-Test 3.xlsx | 5 - ChangeECN | N
96 | 5-CHG-Std ECN Expedite Approve or Reject-Test 4.xlsx | 5 - ChangeECN | N
97 | 5-CHG-Std ECN for Div Part with BOM-Test 1.xlsx | 5 - ChangeECN | Y | High (10) |  |  | February 28 | Rodji | DONE | 16
98 | 5-CHG-Std ECN for Div Part with BOM-Test 2.xlsx | 5 - ChangeECN | Y |  |  |  | February 28 | Rodji | FOR CLARIFICATION | 9 | YES | Based on the description of this Test Case ECN should fail. However in the step 16 it passes validation.
99 | 5-CHG-Std ECN for Div Part with BOM-Test 3.xlsx | 5 - ChangeECN | N
100 | 5-CHG-Std ECN for Div Part with BOM-Test 4.xlsx | 5 - ChangeECN | Y | High (10) |  |  | February 28 | Rodji | DONE | 5
101 | 5-CHG-Std ECN for Div Part with BOM-Test 5.xlsx | 5 - ChangeECN | Y | High (10) |  |  | February 28 | Rodji | DONE | 5 |  | Skipped Step #9 and #10 . No design document stated in the test script that has been revised.
102 | 5-CHG-Std ECN for Div Part with BOM-Test 6.xlsx | 5 - ChangeECN | Y | High (10) |  |  | February 28 | Rodji | DONE | 5 |  | Skipped Step #9 and #10 . No design document stated in the test script that has been revised.
103 | 5-CHG-Std ECN for Div Part with BOM-Test 7.xlsx | 5 - ChangeECN | Y | High (10) |  |  | February 28 | Rodji | DONE | 5
104 | 5-CHG-Std ECN for Div Part with BOM-Test 8.xlsx | 5 - ChangeECN | Y | High (10) |  |  | February 28 | Rodji | DONE | 5
105 | 5-CHG-Std ECN for Div Part with BOM-Test 9.xlsx | 5 - ChangeECN | Y | High (10) |  |  | February 28 | Rodji |  | 5
106 | 5-CHG-Std ECN for Div Parts-Test 1.xlsx | 5 - ChangeECN | N
107 | 5-CHG-Std ECN for Div Parts-Test 2.xlsx | 5 - ChangeECN | N
108 | 5-CHG-Std ECN for Div Parts-Test 3.xlsx | 5 - ChangeECN | N
109 | 5-CHG-Std ECN for Div Parts-Test 4.xlsx | 5 - ChangeECN | Y |  |  |  | February 28 | Rodji |  | 6
110 | 5-CHG-Std ECN for Div Parts-Test 5.xlsx | 5 - ChangeECN | Y | High (10) |  |  | February 28 | Rodji |  | 6
111 | 5-CHG-Std ECN for Div Parts-Test 6.xlsx | 5 - ChangeECN | Y | High (10) |  |  | February 28 | Rodji |  | 6
112 | 5-CHG-Std ECN for Div Parts-Test 7.xlsx | 5 - ChangeECN | Y | High (10) |  |  | February 28 | Rodji |  | 6
113 | 5-CHG-Std ECN for Div Parts-Test 8.xlsx | 5 - ChangeECN | Y | High (10) |  |  | February 28 | Rhey | IN PROGRESS | 4 | There's no 093-101-01 Rev B,1,1
114 | 5-CHG-Std ECN for Div PCBA Parts with BOM-Test 1.xlsx | 5 - ChangeECN | Y |  |  |  | February 28 | Rhey | DONE
115 | 5-CHG-Std ECN for Div PCBA Parts with BOM-Test 2.xlsx | 5 - ChangeECN | Y |  |  |  | February 28 | Rhey | IN PROGRESS | 4
116 | 5-CHG-Std ECN for Div PCBA Parts with BOM-Test 3.xlsx | 5 - ChangeECN | Y |  |  |  | February 28 | Rhey | DONE
117 | 5-CHG-Std ECN for Div PCBA Parts with BOM-Test 4.xlsx | 5 - ChangeECN | Y | High (10) |  |  | February 28 | Rhey | DONE
118 | 5-CHG-Std ECN for Div PCBA Parts with BOM-Test 5.xlsx | 5 - ChangeECN | Y | High (10) |  |  | February 28 | Rhey |  | 4
119 | 5-CHG-Std ECN for Div PCBA Parts with BOM-Test 6.xlsx | 5 - ChangeECN | Y | High (10) |  |  | February 28 | Rhey |  | 4
120 | 5-CHG-Std ECN for Div PCBA Parts with BOM-Test 7.xlsx | 5 - ChangeECN | Y | High (10) |  |  | February 28 | Rhey |  | 4
121 | 5-CHG-Std ECN Reassign a Task-Test 1.xlsx | 5 - ChangeECN | Y |  |  |  | February 28 | Rhey | DONE
122 | 5-CHG-Std ECN Reassign a Task-Test 2.xlsx | 5 - ChangeECN | Y |  |  |  | February 28 | Rhey | DONE
123 | 5-CHG-Std ECN Reassign a Task-Test 3.xlsx | 5 - ChangeECN | Y |  |  |  | February 28 | Rhey | DONE
124 | 5-CHG-Std ECN Review Co-Req Author Changes-Test 1.xlsx | 5 - ChangeECN | Y |  |  |  | February 28 | Rhey | DONE
125 | 5-CHG-Std ECN Review Task-Test 1.xlsx | 5 - ChangeECN | Y |  |  |  | February 28 | Rhey | DONE
126 | 5-CHG-Std ECN Review Task-Test 2.xlsx | 5 - ChangeECN | Y |  |  |  | February 28 | Rhey | DONE
127 | 5-CHG-Std ECN Rework rejected ECN-Test 1.xlsx | 5 - ChangeECN | Y |  |  |  | February 28 | Rhey | DONE
128 | 5-CHG-Std ECN Set Out of Office-Test 1.xlsx | 5 - ChangeECN | Y |  |  |  | February 28 | Rhey | DONE
129 | 5-CHG-Std ECN UI-Test 1.xlsx | 5 - ChangeECN | N
130 | 5-CHG-Std ECN with Co-Req Author assignment-Test 1.xlsx | 5 - ChangeECN | Y |  |  |  | February 28 | Rhey | DONE
131 | 5-CHG-Std ECN with Co-Req Author assignment-Test 2.xlsx | 5 - ChangeECN | Y |  |  |  | February 28 | Rhey | DONE
132 | 5-CHG-Std ECN with Co-Req Author assignment-Test 3.xlsx | 5 - ChangeECN | Y |  |  |  | February 28 | Rhey | DONE
133 | 5-CHG-Std ECN Workflow for a PCBA with Design Doc Task-Test 1.xlsx | 5 - ChangeECN | Y | High (10) |  |  | February 28 | Rhey |  | 16
134 | 5-CHG-Std ECN Workflow for Part with Design Document-Test 1.xlsx | 5 - ChangeECN | Y | High (10) |  |  | February 28 | Rhey |  | 16
135 | 6-CHG-Release ECN UI-Test 1.xlsx | 6 - ReleaseECN | N
136 | 6-Create a Release ECN to change a Parts item status from Preprod to Prod-Test 1.xlsx | 6 - ReleaseECN | Y | High (10) |  |  | January 31 | Rodji | DONE
137 | 6-Create a Release ECN to change a Parts item status from Preprod to Prod-Test 2.xlsx | 6 - ReleaseECN | Y |  |  |  | January 31 | Rodji | DONE
138 | 6-Create a Release ECN to change a Parts item status from Preprod to Prod-Test 3.xlsx | 6 - ReleaseECN | Y | High (10) |  |  | January 31 | Rodji | DONE
139 | 6-Create a Release ECN to change a Parts item status from Preprod to Prod-Test 4.xlsx | 6 - ReleaseECN | Y |  |  |  | January 31 | Rodji | DONE
140 | 6-Create a Release ECN to change a Parts item status from Preprod to Prod-Test 5.xlsx | 6 - ReleaseECN | N
141 | 6-Create a Release ECN to change a Parts item status from Preprod to Prod-Test 6.xlsx | 6 - ReleaseECN | Y |  |  |  | January 31 | Rodji | DONE |  | YES | Need to know the user that has the rights to add BOM (979-467-22) inorder to simulate this scenario
142 | 6-Create a Release ECN to change a Parts item status from Proto to Preprod-Test 1.xlsx | 6 - ReleaseECN | Y | High (10) |  | January 27 | January 31 | Rodji | DONE
143 | 6-Create a Release ECN to change a Parts item status from Proto to Preprod-Test 2.xlsx | 6 - ReleaseECN | Y | High (10) |  | January 27 | January 31 | Rodji | DONE
144 | 6-Create a Release ECN to change a Parts item status from Proto to Preprod-Test 3.xlsx | 6 - ReleaseECN | Y |  |  | January 27 | January 31 | Rodji | DONE
145 | 6-Create a Release ECN to change a Parts item status from Proto to Preprod-Test 4.xlsx | 6 - ReleaseECN | Y |  |  | January 27 | January 31 | Rodji | DONE
146 | 6-Create a Release ECN to change a Parts item status from Proto to Preprod-Test 5.xlsx | 6 - ReleaseECN | Y |  |  | January 27 | January 31 | Rodji | DONE
147 | 6-Create a Release ECN to change a Parts item status from Proto to Preprod-Test 6.xlsx | 6 - ReleaseECN | N
148 | 6-Create a Release ECN to change a Parts item status from Proto to Preprod-Test 7.xlsx | 6 - ReleaseECN | N
149 | 6-Create a Release ECN to change a Parts item status from Proto to Prod-Test 1.xlsx | 6 - ReleaseECN | Y | High (10) |  | January 27 | January 31 | Rodji | DONE |  | YES | PCB and Revision fields are stated in the Test Script but can't find in Release ECN form
150 | 6-Create a Release ECN to change a Parts item status from Proto to Prod-Test 2.xlsx | 6 - ReleaseECN | Y |  |  | January 27 | January 31 | Rodji | DONE |  | YES | Create Document : Document Type "Cable" not existing in dropdown Fields "PCB and Revision" not exist on Release ECN form
151 | 6-Create a Release ECN to change a Parts item status from Proto to Prod-Test 3.xlsx | 6 - ReleaseECN | Y | High (10) |  |  | January 31 | Rodji | DONE
152 | 6-Create a Release ECN to change a Parts item status from Proto to Prod-Test 4.xlsx | 6 - ReleaseECN | Y |  |  |  | January 31 | Rodji | DONE
153 | 6-Create a Release ECN to change a Parts item status from Proto to Prod-Test 5.xlsx | 6 - ReleaseECN | N
154 | 6-Create a Release ECN to change a Parts item status from Proto to Prod-Test 6.xlsx | 6 - ReleaseECN | N
155 | 14-SC-Upload IPC and Compliance Check wf-Test 2.xlsx | 14 - SubstanceCompliance | Y | Medium (5) |  |  | April 30
156 | 14-SC-Upload IPC and Compliance Check wf-Test 3.xlsx | 14 - SubstanceCompliance | Y | Medium (5) |  |  | April 30
157 | 14-SC-Upload IPC and Compliance Check wf-Test 4.xlsx | 14 - SubstanceCompliance |  | Medium (5)
158 | 14-SC-Upload IPC and Compliance Check wf-Test 5.xlsx | 14 - SubstanceCompliance |  | Medium (5)
159 | 14-SC-Upload IPC and Compliance Check wf-Test 6.xlsx | 14 - SubstanceCompliance
160 | 7-CHG-ProtoBOM ECN UI-Test 1.xlsx | 7 - ProtoBOMECN | N
161 | 7-PBOM-ECN to Create BOM for a New Unreleased Part-Test 1.xlsx | 7 - ProtoBOMECN | Y | High (10) |  |  | February 28 | Rhey | DONE |  | I skip upload BOM using NPI BOM loader because its WEB side
162 | 7-PBOM-ECN to Create BOM for a New Unreleased Part-Test 2.xlsx | 7 - ProtoBOMECN | Y |  |  |  | February 28 | Rhey | DONE |  | I skip upload BOM using NPI BOM loader because its WEB side
163 | 7-PBOM-ECN to Create BOM for a New Unreleased Part-Test 3.xlsx | 7 - ProtoBOMECN | Y |  |  |  | February 28 | Rhey | DONE |  | I skip upload BOM using NPI BOM loader because its WEB side
164 | 7-PBOM-ECN to Create BOM for a New Unreleased Part-Test 4.xlsx | 7 - ProtoBOMECN | N
165 | 7-PBOM-ECN to Create BOM for a New Unreleased Part-Test 5.xlsx | 7 - ProtoBOMECN | Y |  |  |  | February 28 | Rhey | DONE |  | I skip upload BOM using NPI BOM loader because its WEB side
166 | 7-PBOM-ECN to Create BOM for a New Unreleased Part-Test 6.xlsx | 7 - ProtoBOMECN | N
167 | 7-PBOM-ECN to Revise a PCBA-Test 1.xlsx | 7 - ProtoBOMECN | Y | High (10) |  |  | February 28 | Rhey | DONE |  | I skip upload BOM using NPI BOM loader because its WEB side
168 | 7-PBOM-ECN to Revise a PCBA-Test 2.xlsx | 7 - ProtoBOMECN | Y | High (10) |  |  | February 28 | Rhey | DONE |  | I skip upload BOM using NPI BOM loader because its WEB side
169 | 8-DV-Deviation Workflow-Test 1.xlsx | 8 - Deviation | Y | High (10) |  |  | April 30
170 | 8-DV-Deviation Workflow-Test 2.xlsx | 8 - Deviation | Y | High (10) |  |  | April 30
171 | 8-DV-Deviation Workflow-Test 3.xlsx | 8 - Deviation
172 | 8-DV-Deviation Workflow-Test 4.xlsx | 8 - Deviation |  | High (10)
173 | 8-DV-Deviation Workflow-Test 5.xlsx | 8 - Deviation
174 | 8-DV-Deviation Workflow-Test 6.xlsx | 8 - Deviation
176 | 9-PCN-Commodity Engineer Recieved Task From TcUA-Test 1.xlsx | 9 - PCN
177 | 9-PCN-Commodity Engineer Recieved Task From TcUA-Test 2.xlsx | 9 - PCN
178 | 9-PCN-Create PCN as PCN Coordinator Role-Test 1.xlsx | 9 - PCN | Y | Low (2) |  |  | May 31
179 | 9-PCN-Create PCN as user other than PCN Coordinator-Test 2.xlsx | 9 - PCN
180 | 10-ECN SUMMARY-Tech Review | 10 - ECNSummaryReport | Y | Low (2) |  |  | May 31
181 | 10-ECN SUMMARY-Change Board | 10 - ECNSummaryReport | Y | Low (2) |  |  | May 31
182 | 10-ECN SUMMARY-Complete with parts and documents | 10 - ECNSummaryReport | Y | Low (2) |  |  | May 31
183 | 10-ECN SUMMARY-Complete with reference designators | 10 - ECNSummaryReport | Y |  |  |  | February 28 | Marjorie | DONE
184 | 10-ECN SUMMARY-Authoring | 10 - ECNSummaryReport | N
185 | 10-ECN SUMMARY-Rejected | 10 - ECNSummaryReport | N
186 | 10- Legacy ECN SUMMARY Report | 10 - ECNSummaryReport | Y | Low (2) |  |  | May 31
187 | 10-ECN SUMMARY-Cancelled | 10 - ECNSummaryReport | N
188 | 11-EFF-Revise Effectivity date for a Released ECN | 11 - ReviseEffectivity | Y | High (10) |  |  | February 28 | Marjorie | DONE
189 | 11-EFF-Revise Effectivity dates out of order for a Released ECN with multiple future ECN against same part | 11 - ReviseEffectivity | Y | High (10) |  |  | February 28 | Marjorie |  | 6
190 | 11-EFF-Revise Effectivity dates in sequential for a Released ECN with multiple future ECN against same part | 11 - ReviseEffectivity | Y | High (10) |  |  | February 28 | Marjorie |  | 6
191 | 11-EFF-Revise Effectivity for a Released ECN date to yesterday | 11 - ReviseEffectivity | Y |  |  |  | February 28 | Marjorie |  | 6
192 | 11-EFF- Business CChange Admin Revise Effectivity for a Released ECN | 11 - ReviseEffectivity | Y | High (10) |  |  | February 28 | Marjorie | DONE
193 | 11-EFF- User other than Planner/Change Admin Revise Effectivity for a Released ECN | 11 - ReviseEffectivity | Y |  |  |  | February 28 | Marjorie | DONE
194 | 12-Transferring of parts for just one commodity level 1 | 12 - SupplierTransfer
195 | 12-Transferring a vendor for more than one commodity level 1 code | 12 - SupplierTransfer | Y | Medium (5) |  |  | April 30
196 | 12- Transferring for 2 Commodity Level 1 codes | 12 - SupplierTransfer
197 | 12-Supplier Transfer Request as user in wrong role | 12 - SupplierTransfer
198 | 12-Transferring just one commodity level 1 request that is rejected | 12 - SupplierTransfer | Y |  |  |  | April 30
199 | 12-Transferring vendor parts to another vendor | 12 - SupplierTransfer | Y |  |  |  | April 30
200 | 13-CE- Commodity Engineer Transfer Request Workflow -Test 1 | 13 - CommEnggTransfer | Y | Medium (5) |  |  | April 30
201 | 13-CE- Commodity Engineer Transfer Request Workflow -Test 2 | 13 - CommEnggTransfer
202 | 13-CE- Commodity Engineer Transfer Request Workflow-Test 3.xlsx | 13 - CommEnggTransfer
203 | 14-SC-Apply an Exemption-Test 1.xlsx | 14 - SubstanceCompliance | Y | Low (2) |  |  | May 31
204 | 14-SC-Calculation for AVL Change-Test 1.xlsx | 14 - SubstanceCompliance
206 | 14-SC-Calculation for AVL Change-Test 3.xlsx | 14 - SubstanceCompliance | Y |  |  |  | April 30
207 | 14-SC-Calculation for AVL Change-Test 4.xlsx | 14 - SubstanceCompliance
208 | 14-SC-Calculation for AVL Change-Test 5.xlsx | 14 - SubstanceCompliance
209 | 14-SC-Calculation for AVL Change-Test 6.xlsx | 14 - SubstanceCompliance
210 | 14-SC-Calculation for AVL Change-Test 7.xlsx | 14 - SubstanceCompliance
211 | 14-SC-Calculation for AVL Change-Test 8.xlsx | 14 - SubstanceCompliance
212 | 14-SC-Change Attribute Data-Test 1.xlsx | 14 - SubstanceCompliance | Y | Low (2) |  |  | May 31
216 | 14-SC-Change Attribute Data-Test 5.xlsx | 14 - SubstanceCompliance
217 | 14-SC-Change Attribute Data-Test 6.xlsx | 14 - SubstanceCompliance |  | Low (2)
218 | 14-SC-Change Attribute Data-Test 7.xlsx | 14 - SubstanceCompliance
219 | 14-SC-Change Attribute Data-Test 8.xlsx | 14 - SubstanceCompliance
220 | 14-SC-Change Attribute Data-Test 9.xlsx | 14 - SubstanceCompliance
221 | 14-SC-Change Attribute Data-Test 10.xlsx | 14 - SubstanceCompliance
222 | 14-SC-Change Attribute Data-Test 11.xlsx | 14 - SubstanceCompliance
225 | 14-SC-Change Attribute Data-Test 14.xlsx | 14 - SubstanceCompliance
228 | 14-SC-Create a Material-Test 1.xlsx | 14 - SubstanceCompliance
229 | 14-SC-Create a Substance-Test 1.xlsx | 14 - SubstanceCompliance
230 | 14-SC-Manually Invoking RoHS Compliancy Status Recalculation-Test 1.xlsx | 14 - SubstanceCompliance | Y | Medium (5) |  |  | April 30
231 | 14-SC-Manually Invoking RoHS Compliancy Status Recalculation-Test 2.xlsx | 14 - SubstanceCompliance |  | Medium (5)
232 | 14-SC-Relate Material to Part-Test 1.xlsx | 14 - SubstanceCompliance
233 | 14-SC-Relate Substances to Material-Test 1.xlsx | 14 - SubstanceCompliance
234 | 14-SC-Supplier Transfer-Test 1.xlsx | 14 - SubstanceCompliance |  | Low (2)
235 | 14-SC-Upload IPC and Compliance Check wf-Test 1.xlsx | 14 - SubstanceCompliance
236 | 23-DOC-ECO Document | 23 - DocumentManagement
237 | 23-DOC-GENERAL DOCUMENT-Process Specification | 23 - DocumentManagement | N
238 | 23-DOC-GENERAL DOCUMENT-Manual | 23 - DocumentManagement
239 | 23-DOC-GENERAL DOCUMENT-Certificate | 23 - DocumentManagement
240 | 22-DOC-ITAR Form-Test 1.xlsx | 22 - Security
244 | 16-RPT-BOM COMPARE | 16 - SearchAndReports | Y | High (10) |  |  | March 31
245 | 16-SER-BRANCH FAMILY | 16 - SearchAndReports | Y |  |  |  | March 31
246 | 16-SER-Simple Search Existing Discontinuance Notice | 16 - SearchAndReports | Y |  |  |  | March 31
247 | 16-SER-Simple Search non-Existing Discontinuance Notice | 16 - SearchAndReports | Y |  |  |  | March 31
248 | 16-SER-Search for existing design document and Document creator | 16 - SearchAndReports | Y | Low (2) |  |  | May 31
249 | 16-SER-Search for non-existing design document and Document creator #2 | 16 - SearchAndReports | Y |  |  |  | March 31
250 | 16-SER-search for DTG Model Modify request by request number and by request creator | 16 - SearchAndReports | Y |  |  |  | March 31
251 | 16-SER-Search for DTG Model request by request number and by request creator | 16 - SearchAndReports | Y |  |  |  | March 31
252 | 16-SER-Simple Search by ECN ATTRIBUTES- Available in UA | 16 - SearchAndReports | Y | High (10) |  |  | March 31
253 | 16-SER-Simple Search by ECN ATTRIBUTES- Not Available in UA | 16 - SearchAndReports | Y |  |  |  | March 31
254 | 16-SER-LEAF FAMILY | 16 - SearchAndReports | Y |  |  |  | March 31
255 | 16-SER- Existing PART REQUEST | 16 - SearchAndReports | Y | Low (2) |  |  | May 31
256 | 16-SER- Non-Existing PART REQUEST | 16 - SearchAndReports | Y |  |  |  | March 31
257 | 16-SER-Quick Search-ECN Creator | 16 - SearchAndReports | Y |  |  |  | March 31
258 | 16-SER-Quick Search-Part Request Creator | 16 - SearchAndReports | Y | Low (2) |  |  | May 31
259 | 16-SER-Quick Search-Document Creator | 16 - SearchAndReports | Y |  |  |  | March 31
260 | 16-SER-Quick Search-Part responsible party | 16 - SearchAndReports | Y |  |  |  | March 31
261 | 16-SER-Quick Search-Part Number | 16 - SearchAndReports | Y | Low (2) |  |  | May 31
262 | 16-SER-Quick Search-Non-existing Part Number | 16 - SearchAndReports | Y |  |  |  | March 31
263 | 16-SER-Quick Search-Part Decription | 16 - SearchAndReports | Y | Low (2) |  |  | May 31
264 | 16-SER-Quick Search-Document Name | 16 - SearchAndReports | Y | Low (2) |  |  | May 31
265 | 16-SER-Quick Search-Non-existing ECN number | 16 - SearchAndReports | Y |  |  |  | March 31
266 | 16-SER-Quick Search-Task Number | 16 - SearchAndReports | Y |  |  |  | March 31
267 | 16-SER-Quick Search-Device Package Name | 16 - SearchAndReports | Y |  |  |  | March 31
268 | 16-SER-SUPPLIER PART TRANSFER | 16 - SearchAndReports | Y |  |  |  | March 31
269 | 16-SER-TAG REQUEST Attributes | 16 - SearchAndReports | Y |  |  |  | March 31
270 | 16-SER-TERADYNE PART ATTRIBUTES | 16 - SearchAndReports | Y | Medium (5) |  |  | March 31
271 | 16-SER-TERADYNE PART ATTRIBUTES-Multi Attributes | 16 - SearchAndReports | Y | Medium (5) |  |  | March 31
272 | 16-SER-TERADYNE PART ATTRIBUTES-Negative | 16 - SearchAndReports | Y |  |  |  | March 31
273 | 16-SER-Existing TERADYNE PART number | 16 - SearchAndReports | Y |  |  |  | March 31
274 | 16-SER-Existing TERADYNE PART number - export | 16 - SearchAndReports | Y | Medium (5) |  |  | March 31
275 | 16-SER-Non-Existing TERADYNE PART number | 16 - SearchAndReports | Y |  |  |  | March 31
276 | 16-SER-Commercial Part search for VENDOR PART and VP part number | 16 - SearchAndReports | Y | Low (2) |  |  | May 31
277 | 16-SER-Non-Existing Commercial Part search for VENDOR PART and VP part number | 16 - SearchAndReports | Y |  |  |  | March 31
279 | 18-CPR-Classify a Part-migrated comm part | 18 - VendorManagement
280 | 18-CPR-Classify a Part-migrated div part | 18 - VendorManagement
281 | 18-CPR-Classify a Part-Comm Part to Open Deviation | 18 - VendorManagement
282 | 18-CPR-Classify a Part-Div Part to Open Deviation | 18 - VendorManagement
283 | 18-CPR-Classify a Part-Comm Part in BOM associated to open ECN | 18 - VendorManagement
284 | 18-CPR-Classify a Part-Div Part in BOM associated to open ECN | 18 - VendorManagement
285 | 18-CPR-Classify a Part-Div Part in BOM associated to open ECN as an impacted item | 18 - VendorManagement
288 | 18-VM-Vendor Part Creation-Comm Part in BOM of Open ECN | 18 - VendorManagement
289 | 18-VM-Vendor Part Creation-Comm Part related to Open Deviation | 18 - VendorManagement
290 | 18-VM-Vendor Part Creation-Div Part Related to Open Deviation | 18 - VendorManagement
291 | 18-VM-Vendor Part Creation-Div Part in BOM thats revised but not released | 18 - VendorManagement
292 | 18-VM-Vendor Creation-Using migrated Div and Comm Part | 18 - VendorManagement
293 | 18-VM-Vendor Part Modify-related to migrated Comm and Vendor Part | 18 - VendorManagement
294 | 18-VM-Vendor Part Modify-related to migrated Div and Vendor Part | 18 - VendorManagement
295 | 18-VM-Vendor Part Modify-Comm Part in BOM of an Open ECN | 18 - VendorManagement
296 | 18-VM-Vendor Part Modify-Comm Part related to Open Deviation | 18 - VendorManagement
297 | 18-VM-Vendor Part Modify-Div Part related to Open Deviation | 18 - VendorManagement
298 | 18-VM-Vendor Part Modify-Div Part in BOM of an Open ECN | 18 - VendorManagement
299 | 18-VM-Vendor Part Modify-Div Part in Solution Items of an Open ECN | 18 - VendorManagement |  | Low (2)
300 | 19-AWC-Filters and Refiners for Commercial Part | 19 - ActiveWorkspace
301 | 19-AWC-Filters and Refiners for Deviation | 19 - ActiveWorkspace
302 | 19-AWC-Filters and Refiners for Design Doc | 19 - ActiveWorkspace
303 | 19-AWC-Filters and Refiners for Discontinuance Doc | 19 - ActiveWorkspace
304 | 19-AWC-Filters and Refiners for Divisional Part | 19 - ActiveWorkspace
305 | 19-AWC-Filters and Refiners for General Doc | 19 - ActiveWorkspace
306 | 19-AWC-Filters and Refiners for a Part Modifier Request | 19 - ActiveWorkspace
307 | 19-AWC-Filters and Refiners for Part Request | 19 - ActiveWorkspace
308 | 19-AWC-Filters and Refiners for a PCN | 19 - ActiveWorkspace
309 | 19-AWC-Filters and Refiners for ProtoBOM ECN | 19 - ActiveWorkspace
310 | 19-AWC-Filters and Refiners for Release ECN | 19 - ActiveWorkspace
311 | 19-AWC-Filters and Refiners for Standard ECN | 19 - ActiveWorkspace
312 | 19-AWC-Filters and Refiners for TAG Model Create Request | 19 - ActiveWorkspace
313 | 19-AWC-Filters and Refiners for TAG Model Modify Request | 19 - ActiveWorkspace
314 | 19-AWC-Filters and Refiners for Vendor Part | 19 - ActiveWorkspace
315 | 19-AWC-Search items by user | 19 - ActiveWorkspace
316 | 19-AWC- Export an item found through search | 19 - ActiveWorkspace
317 | 23-DOC-DESIGN DOCUMENT-Schematic | 23 - DocumentManagement | N
318 | 23-DOC-DESIGN DOCUMENT-Assembly | 23 - DocumentManagement | Y | Low (2) |  |  | May 31
319 | 23-DOC-DESIGN DOCUMENT-Piece Part Word Doc | 23 - DocumentManagement | N
320 | 23-DOC-DESIGN DOCUMENT-Piece Part Zip File | 23 - DocumentManagement | N
321 | 23-DOC-DESIGN DOCUMENT-Engineering Layout | 23 - DocumentManagement
322 | 30-BOM full explosion with RoHS compliance status | 30 - TcRA Reports | Y | Low (2) |  |  | May 31
323 | 30-BOM MTBFReport | 30 - TcRA Reports | Y | Low (2) |  |  | May 31
324 | 30-BOM RoHS Report | 30 - TcRA Reports | Y | Low (2) |  |  | May 31
327 | 30-Part Qualification Report | 30 - TcRA Reports | Y | Low (2) |  |  | May 31
328 | 32-IT TCRA Reports-AuthorConsumerReports | 32 - Support Reports
329 | 32-IT TCRA Reports-DailyLogin | 32 - Support Reports
330 | 32-IT TCRA Reports-ECN Metrics (entire set) | 32 - Support Reports
331 | 35-PST- Export Results to Excel | 35 - Part Selection Tool (PST) | Y | Medium (5) |  |  | March 31
332 | 23-DN-Discontinuance Notice Create-User in wrong role | 23 - DocumentManagement
333 | 23-DN-Discontinuance Notice Create-Validations | 23 - DocumentManagement |  | Medium (5)
334 | 23-DN-Discontinuance Notice Create-Status of Obsolete or Removed | 23 - DocumentManagement | Y | Medium (5) |  |  | May 31
335 | 23-DN-Discontinuance Notice Create-Status' of null and obsolete | 23 - DocumentManagement | Y |  |  |  | May 31
336 | 23-DN-Discontinuance Notice Create-Status of Removed and Obsolete | 23 - DocumentManagement | Y | Medium (5) |  |  | May 31
337 | 23-DN-Discontinuance Notice Create-Neither status is obsolete or removed | 23 - DocumentManagement |  | Medium (5)
338 | 23-DN-Discontinuance Notice Edit-User in correct role | 23 - DocumentManagement | Y |  |  |  | May 31
339 | 23-DN-Discontinuance Notice Edit-User in wrong role | 23 - DocumentManagement
340 | 23-DP-Create a Device Package-User in correct role | 23 - DocumentManagement | Y | Low (2) |  |  | May 31
341 | 23-DP-Create a Device Package-User in wrong role | 23 - DocumentManagement |  | Low (2)
342 | 23-DP-Relate Device Package to a commercial Part | 23 - DocumentManagement | Y | Low (2) |  |  | May 31
343 | 29-PLS- Part List Search-Test 1.xlsx | 29 - Part List Search (PLS) | Y | Medium (5) |  |  | March 31
344 | 30-Commercial Part DFM Report 2 | 30 - TcRA Reports | Y | Low (2) |  |  | May 31
345 | 30-Commercial Part Reliability Report 5 | 30 - TcRA Reports | Y | Low (2) |  |  | May 31
346 | 30-Commercial Part Report 2 | 30 - TcRA Reports | Y | Low (2) |  |  | May 31
347 | 30-DPMO Properties by Part Number | 30 - TcRA Reports | Y | Low (2) |  |  | May 31
348 | 30-PCB Commercial Parts | 30 - TcRA Reports | Y | Low (2) |  |  | May 31
349 | 30-BOM Agreed to pricing and Demand Report | 30 - TcRA Reports | Y | Low (2) |  |  | May 31
350 | 30-BOM full explosion RoHS Report | 30 - TcRA Reports | Y | Low (2) |  |  | May 31
351 | 30-BOM full explosion with Manufacturer and Supplier Info | 30 - TcRA Reports | Y | Low (2) |  |  | May 31
352 | 30-BOM full explosion with Related Documents | 30 - TcRA Reports | Y | Low (2) |  |  | May 31
353 | 16-RPT-BOM WITH DOCUMENTS Report | 16 - SearchAndReports | Y | Low (2) |  |  | May 31
354 | 16-RPT-BOM WITH ITEM STATUS Report | 16 - SearchAndReports | N
355 | 16-RPT-BOM WITH SUPPLIER Report | 16 - SearchAndReports | Y | Low (2) |  |  | May 31
356 | 16-RPT-INVENTORY CHECKLIST Report | 16 - SearchAndReports | N
359 | 28-Upload a compact bom with Quotes "" | 28 - NPI BOM Loader | Y | High (10) |  |  | March 31
360 | 28-Upload an Expanded BOM | 28 - NPI BOM Loader | Y | High (10) |  |  | March 31
361 | 28-Upload a BOM without refdes | 28 - NPI BOM Loader | Y | High (10) |  |  | March 31
362 | 28-Upload a BOM to a non-working part | 28 - NPI BOM Loader | Y |  |  |  | March 31
363 | 28-Upload a BOM with a bad child | 28 - NPI BOM Loader | Y |  |  |  | March 31
364 | 28-Upload a BOM with a quantity less than the refdes | 28 - NPI BOM Loader | Y |  |  |  | March 31
365 | 28-Upload a BOM with quantity greater than number of refdes | 28 - NPI BOM Loader | Y | High (10) |  |  | March 31
366 | 28-Upload BOM with missing assembly | 28 - NPI BOM Loader | Y |  |  |  | March 31
367 | 28-Upload BOM with bad header file name | 28 - NPI BOM Loader | Y |  |  |  | March 31
368 | 28-Upload BOM with bad header format-lower case | 28 - NPI BOM Loader | Y |  |  |  | March 31
369 | 28-Upload BOM with bad item format | 28 - NPI BOM Loader | Y |  |  |  | March 31
370 | 28-Upload BOM with User that does not have TC account | 28 - NPI BOM Loader | Y |  |  |  | March 31
371 | 28-Upload BOM using wrong Password | 28 - NPI BOM Loader | Y |  |  |  | March 31
372 | 28-Upload BOM as User with Consumer Access | 28 - NPI BOM Loader | Y |  |  |  | March 31
373 | 28-Upload a BOM with no user name | 28 - NPI BOM Loader | Y |  |  |  | March 31
374 | 32-Usage Report-Author/Consumer logins per week | 32 - Support Reports | Y |  |  |  | May 31
375 | IT-TCRA BOM Compare Report (oracle) | 32 - Support Reports
376 | 32-ECN Metrics Report | 32 - Support Reports
377 | 32-ECN Data for Engineering | 32 - Support Reports
378 | 32-ECN Support-AuthorConsumerReports | 32 - Support Reports
379 | 28-Upload BOM with no password | 28 - NPI BOM Loader | Y |  |  |  | March 31
380 | 28-Upload BOM with no BOM file name | 28 - NPI BOM Loader | Y |  |  |  | March 31
381 | 28-Upload BOM with no refdes flag | 28 - NPI BOM Loader | Y |  |  |  | March 31
382 | 28-Upload BOM into a Commodity Part | 28 - NPI BOM Loader | Y |  |  |  | March 31
383 | 28-Upload a BOM into an assembly where the assembly is listed in the BOM - Circular reference | 28 - NPI BOM Loader | Y |  |  |  | March 31
384 | 28-Upload a BOM with some quantity of REFDES and additional parts without refdes | 28 - NPI BOM Loader | Y | High (10) |  |  | March 31
385 | 28-Upload a non-CSV BOM | 28 - NPI BOM Loader | Y |  |  |  | March 31
386 | 28-Upload BOM with missing commas | 28 - NPI BOM Loader | Y |  |  |  | March 31
387 | 28-Upload BOM with extra commas | 28 - NPI BOM Loader | Y | High (10) |  |  | March 31
388 | 28-Upload BOM with extra header field | 28 - NPI BOM Loader | Y | High (10) |  |  | March 31
389 | 28-Upload a BOM with zero quantity item | 28 - NPI BOM Loader | Y | High (10) |  |  | March 31
390 | 28-Upload a packed BOM similar to existing PCBA BOM | 28 - NPI BOM Loader | Y | High (10) |  |  | March 31
391 | 28-Upload a flat BOM similar to existing PCBA BOM | 28 - NPI BOM Loader | Y | High (10) |  |  | March 31
392 | 28-Upload BOM with non-Adjacent item | 28 - NPI BOM Loader | Y | High (10) |  |  | March 31
393 | 28-Verify ranging in packed view | 28 - NPI BOM Loader | Y | High (10) |  |  | March 31
394 | 28-Verify ranging in packed view with Alpha refdes | 28 - NPI BOM Loader | Y | High (10) |  |  | March 31
395 | 28-Verify refdes ordering | 28 - NPI BOM Loader | Y | High (10) |  |  | March 31
396 | 28-Verify behavior if there are spaces in the cells | 28 - NPI BOM Loader | Y | High (10) |  |  | March 31
397 | 28-Upload a BOM with duplicate refdes | 28 - NPI BOM Loader | Y | High (10) |  |  | March 31
398 | 28-Load BOM twice in parallel for assembly in two different browser sessions by two different users | 28 - NPI BOM Loader | Y |  |  |  | March 31
399 | 28-Load BOM twice in parallel for assembly in two different browser sessions by same user | 28 - NPI BOM Loader | Y |  |  |  | March 31
401 | 14-SC-Run ad-hoc queries-Test 2 | 14 - SubstanceCompliance
402 | 14-SC-Run ad-hoc queries-Test 3 | 14 - SubstanceCompliance
403 | 14-SC-Viewing RoHS and Manufacturing Process Attributes and Files-Test 1 | 14 - SubstanceCompliance | Y |  |  |  | April 30
405 | 14-SC-Generate Substance Compliance Reports-Test 2 | 14 - SubstanceCompliance
406 | 28-Multiple assemblies in BOM | 28 - NPI BOM Loader | Y |  |  |  | March 31
407 | 28-Unchanged BOM | 28 - NPI BOM Loader | Y | High (10) |  |  | March 31
408 | 28-Load a large flat PCBA BOM | 28 - NPI BOM Loader | Y | High (10) |  |  | March 31
409 | 28-Load a large Packed PCBA BOM | 28 - NPI BOM Loader | Y | High (10) |  |  | March 31
410 | 01-Div Part - Controlling Business Unit DM-Test 1 | 26 - 227081 Solution Specification - Migration_r05* | Y |  |  |  | April 30
411 | 01-Div Part - Project Value DM-Test 1 | 26 - 227081 Solution Specification - Migration_r05* | Y |  |  |  | April 30
413 | 35-PST- Verify Calculations | 35 - Part Selection Tool (PST) | Y | Medium (5) |  |  | March 31
414 | 35-PST- Verify behavior of 'RoHS Compliance status' | 35 - Part Selection Tool (PST) | Y | Medium (5) |  |  | March 31
415 | 35-PST- Verify results match part(s) data in TcUA | 35 - Part Selection Tool (PST) | Y | Medium (5) |  |  | March 31
416 | 35-PST- Verify LOV's and Search Criteria | 35 - Part Selection Tool (PST) | Y | Medium (5) |  |  | March 31
417 | 35-PST- Wild Card Searches | 35 - Part Selection Tool (PST) | Y | Medium (5) |  |  | March 31
418 | 35-PST- Part Number Searches | 35 - Part Selection Tool (PST) | Y | Low (2) |  |  | May 31
419 | 35-PST- Internal Part Status Filters | 35 - Part Selection Tool (PST) | Y | Low (2) |  |  | May 31
420 | 35-PST- Supplier Rating Filters | 35 - Part Selection Tool (PST) | Y | Low (2) |  |  | May 31
421 | 9-PCN-Create PCN and add working part-Test 3 | 9 - PCN
423 | 16-SER-SIMPLE SEARCH-Part Request Creator | 16 - SearchAndReports | Y |  |  |  | March 31
424 | 16-WHERE USED Report-Using tool | 16 - SearchAndReports | Y | Medium (5) |  |  | March 31
425 | 23-DOC-DESIGN DOC added into 2 RELEASE ECN's at same time | 23 - DocumentManagement | N
426 | 23-DOC-DESIGN DOC added into 2 Working ECN's at same time | 23 - DocumentManagement | N
430 | 5-CHG-ECN Sign Off Tab-Test 1 | 5 - ChangeECN | Y |  |  |  | February 28 | Marjorie | DONE
431 | 8-DV-Deviation Request Sign Off Tab-Test 1 | 8 - Deviation | Y |  |  |  | April 30
432 | 02-CPR-Commercial Part Create Sign Off Tab | 2 - CommercialPartRequest |  | Low (2)
433 | 02-CPR-DTG Model Modification Request Sign Off Tab | 2 - CommercialPartRequest
434 | 02-CPR-DTG Model Request Sign Off Tab | 2 - CommercialPartRequest
435 | 02-CPR-Part Modify Request Sign Off Tab | 2 - CommercialPartRequest
436 | 02-CPR-TAG Model Create Request Sign Off Tab | 2 - CommercialPartRequest
437 | 02-CPR-TAG Model Modification Request Sign Off Tab | 2 - CommercialPartRequest
438 | 01-Div Part Create - Create Auto Assigned Division Part as Author | 1 - DivisionalPartRequest | Y | High (10) | Complete |  | January 31 |  | Done
439 | 01-Div Part Create - Create Auto Assigned Division Part as Occasional Author | 1 - DivisionalPartRequest | Y |  | Complete |  | January 31 | Marjorie | DONE
441 | 01-Div Part Create - Create a Divisional Part when Part Sub-Category is Unknown | 1 - DivisionalPartRequest | N
442 | 01-Div Part Create - Create a Div Part when no Part Category exists | 1 - DivisionalPartRequest | Y |  | Complete | January 27 | January 31 | Marjorie | DONE
443 | 01-Div Part - Occasional Author edits a Division Part to Change the Part Description | 1 - DivisionalPartRequest | N
444 | 01-Div Part - Author tries to edit a Division Part at PreProduction Status to Change the Part Description | 1 - DivisionalPartRequest | N
445 | 01-Div Part Author tries to edits a Division Part at Production Status to Change the Part Description | 1 - DivisionalPartRequest | N
446 | 01-Div Part - Author edits a Division Part to Change the Part Description | 1 - DivisionalPartRequest | Y | High (10) | Complete |  | January 31 | Marjorie | DONE |  | YES | Used another "Cable" Part Category instead of "HLA" because cannot verify the changes in ECCN since the data is in Stage
447 | 01-Div Part- Planner Assigns Oracle Orgs to newly created Parts | 1 - DivisionalPartRequest | Y | High (10) | Complete |  | January 31 |  | Done
448 | 01-Div Part- Business Change Admin Assigns Oracle Orgs to newly created Parts | 1 - DivisionalPartRequest | Y | High (10) | Complete |  | January 31 |  | Done
449 | 01-Div Part- Planner Assigns a new Oracle Org to exisiting Assembly Part | 1 - DivisionalPartRequest | Y | High (10) | Complete |  | January 31 |  | Done
450 | 01-Div Part- Someone other than Planner tries to Assign an Oracle Org to a part | 1 - DivisionalPartRequest | Y |  | Complete |  | January 31 |  | Done
451 | 01-Div Part Create - Create a dash version of an existing part as an Author | 1 - DivisionalPartRequest | Y | High (10) | Complete |  | January 31 |  | Done
452 | 01-Div Part Create - Create a dash version of an existing part as an Occasional Author | 1 - DivisionalPartRequest | Y |  | Complete |  | January 31 |  | Done
453 | 01-Div Part Create - Create a Dash version when the base number does not exist | 1 - DivisionalPartRequest | Y |  | Complete |  | January 31 |  | Done
454 | 01-Div Part Create - Create a Div Part bypassing auto assign as an Author | 1 - DivisionalPartRequest | Y |  | Complete |  | January 31 |  | Done
455 | 01-Div Part Create - Create a Div Part bypassing auto assign as a Consumer | 1 - DivisionalPartRequest | N
456 | 01-Div Part Create - Create a Div Part bypassing auto assign | 1 - DivisionalPartRequest | Y |  | Complete |  | January 31 |  | Done
457 | 01-Div Part-Oracle 11i Test Scripts SR | 1 - DivisionalPartRequest | Y |  | Oracle |  | January 31 | Marjorie | NA |  |  | Test case in Oracle
459 | 02-CPR-Request Pool | 2 - CommercialPartRequest | Y | Medium (5) | Complete | January 27 | January 31 | Rhey | DONE
460 | 02-CPR-Commercial Part Create Test 1 | 2 - CommercialPartRequest | Y | High (10) | Complete | January 27 | January 31 | Rhey | DONE
461 | 02-CPR-Commercial Part Create Test 2 | 2 - CommercialPartRequest
462 | 02-CPR-Commercial Part Create Test 3 | 2 - CommercialPartRequest
463 | 02-CPR-Commercial Part Create Test 4 | 2 - CommercialPartRequest
464 | 02-CPR-Commercial Part Create Test 5 | 2 - CommercialPartRequest | Y | High (10) | Complete |  | January 31 | Rhey | DONE
465 | 02-CPR-Commercial Part Create Test 6 | 2 - CommercialPartRequest |  | High (10)
466 | 02-CPR-Commercial Part Create Test 7 | 2 - CommercialPartRequest |  | High (10)
467 | 02-CPR-Commercial Part Modify Test 1 | 2 - CommercialPartRequest
468 | 02-CPR-Commercial Part Modify Test 2 | 2 - CommercialPartRequest |  | High (10)
469 | 02-CPR-Commercial Part Modify Test 3 | 2 - CommercialPartRequest
470 | 02-CPR-Commercial Part Modify Test 4 | 2 - CommercialPartRequest
471 | 02-CPR-Commercial Part Modify Test 5 | 2 - CommercialPartRequest
472 | 02-CPR-Commercial Part Modify Test 6 | 2 - CommercialPartRequest
473 | 02-CPR-Commercial Part Modify Test 7 | 2 - CommercialPartRequest
474 | 02-CPR-Commercial Part Modify Test 8 | 2 - CommercialPartRequest
475 | 02-CPR-Commercial Part Modify Test 9 | 2 - CommercialPartRequest
476 | 02-CPR-Commercial Part Modify Test 10 | 2 - CommercialPartRequest
477 | 02-CPR-Commercial Part and Model Request Test 1 | 2 - CommercialPartRequest
478 | 02-CPR-Commercial Part and Model Request Test 2 | 2 - CommercialPartRequest
479 | 02-CPR-Commercial Part and Model Request Test 3 | 2 - CommercialPartRequest
480 | 02-CPR-Commercial Part and Model Request Test 4 | 2 - CommercialPartRequest
481 | 02-CPR-Commercial Part and Model Request Test 5 | 2 - CommercialPartRequest | N
482 | 02-CPR-Commercial Part and Model Request Test 6 | 2 - CommercialPartRequest | N
483 | 02-CPR-Commercial Part and Model Request Test 7 | 2 - CommercialPartRequest
484 | 02-CPR-Commercial Part and Model Request Test 8 | 2 - CommercialPartRequest | N
485 | 02-CPR-Commercial Part and Model Request Test 9 | 2 - CommercialPartRequest | N
486 | 02-CPR-Commercial Part and Model Request Test 10 | 2 - CommercialPartRequest | N
487 | 02-CPR-Commercial Part and Model Request Test 11 | 2 - CommercialPartRequest | N
488 | 02-CPR-Commercial Part and DTG Model Workflow Test 1 | 2 - CommercialPartRequest | Y | High (10) | WIP |  | January 31 | Rhey | DONE
489 | 02-CPR-Commercial Part and DTG Model Workflow Test 2 | 2 - CommercialPartRequest | N
490 | 02-CPR-Commercial Part and DTG Model Workflow Test 3 | 2 - CommercialPartRequest | N
491 | 02-CPR-Commercial Part and DTG Model Workflow Test 4 | 2 - CommercialPartRequest | N
492 | 02-CPR-Commercial Part and DTG Model Workflow Test 5 | 2 - CommercialPartRequest | N
493 | 02-CPR-Commercial Part and DTG Model Workflow Test 6 | 2 - CommercialPartRequest | N
494 | 02-CPR-Commercial Part and DTG Model Workflow Test 7 | 2 - CommercialPartRequest | Y | High (10) | Complete | January 27 | January 31 | Rhey | DONE
495 | 02-CPR-Commercial Part and DTG Model Workflow Test 8 | 2 - CommercialPartRequest | Y |  | Complete | January 27 | January 31 | Rhey | DONE
496 | 02-CPR-Commercial Part and DTG Model Workflow Test 9 | 2 - CommercialPartRequest | N
497 | 02-CPR-Commercial Part and DTG Model Workflow Test 10 | 2 - CommercialPartRequest | N
498 | 02-CPR-Commercial Part and DTG Model Workflow Test 11 | 2 - CommercialPartRequest |  | High (10)
499 | 02-CPR-Commercial Part and DTG Model Workflow Test 12 | 2 - CommercialPartRequest | Y | High (10) | WIP |  | January 31 | Rhey | DONE
500 | 02-CPR-Commercial Part and DTG Model Workflow Test 13 | 2 - CommercialPartRequest
501 | 02-CPR-Classify a Part Test 1 | 2 - CommercialPartRequest |  | Medium (5)
502 | 02-CPR-Classify a Part Test 2 | 2 - CommercialPartRequest | Y | Medium (5) | Complete | January 27 | January 31 | Rhey | DONE
503 | 02-CPR-Classify a Part Test 3 | 2 - CommercialPartRequest | N
504 | 02-CPR-Classify a Part Test 4 | 2 - CommercialPartRequest | N
505 | 02-CPR-Classify a Part Test 5 | 2 - CommercialPartRequest | N | Medium (5)
506 | 02-CPR-Classify a Part Test 6 | 2 - CommercialPartRequest | N
507 | 02-CPR-Classify a Part Test 7 | 2 - CommercialPartRequest | N
509 | 02-CPR-Classify a Part Test 9 | 2 - CommercialPartRequest | N
510 | 02-CPR-Classify a Part Test 10 | 2 - CommercialPartRequest | N
512 | 02-CPR-Classify a Part Test 12 | 2 - CommercialPartRequest | N
513 | 02-CPR-Classify a Part Test 13 | 2 - CommercialPartRequest | N
514 | 02-CPR-Classify a Part Test 14 | 2 - CommercialPartRequest | N
515 | 02-CPR-Classify a Part Test 15 | 2 - CommercialPartRequest | N
516 | 02-CPR-Classify a Part Test 16 | 2 - CommercialPartRequest | N
517 | 02-CPR-Classify a Part Test 17 | 2 - CommercialPartRequest | N
518 | 02-CPR-Classify a Part Test 18 | 2 - CommercialPartRequest | N
519 | 02-CPR-DTG Model Modify Request Test 1 | 2 - CommercialPartRequest | N
520 | 02-CPR-DTG Model Modify Request Test 2 | 2 - CommercialPartRequest | N
521 | 02-CPR-DTG Model Modify Request Test 3 | 2 - CommercialPartRequest | N
522 | 02-CPR-DTG Model Modify Request Test 4 | 2 - CommercialPartRequest | N
523 | 02-CPR-DTG Model Modify Request Test 5 | 2 - CommercialPartRequest | N
524 | 02-CPR-DTG Model Modify Request Test 6 | 2 - CommercialPartRequest | N
526 | 02-CPR-DTG Model wf Test 1 | 2 - CommercialPartRequest | N | Medium (5)
527 | 02-CPR-DTG Model wf Test 2 | 2 - CommercialPartRequest | N
528 | 02-CPR-DTG Model wf Test 3 | 2 - CommercialPartRequest | N
529 | 02-CPR-DTG Model wf Test 4 | 2 - CommercialPartRequest | N
530 | 02-CPR-DTG Model wf Test 5 | 2 - CommercialPartRequest | N
531 | 02-CPR-DTG Model wf Test 6 | 2 - CommercialPartRequest | N
532 | 02-CPR-DTG Model Modeler Work Test 1 | 2 - CommercialPartRequest | N | Medium (5)
533 | 02-CPR-DTG Model Modeler Work Test 2 | 2 - CommercialPartRequest | N
534 | 02-CPR-DTG Model Modeler Work Test 3 | 2 - CommercialPartRequest | N
535 | 02-CPR-DTG Model Modeler Work Test 4 | 2 - CommercialPartRequest | N
536 | 02-CPR-DTG Model Modeler Work Test 5 | 2 - CommercialPartRequest | N
537 | 02-CPR-DTG Model Modeler Work Test 6 | 2 - CommercialPartRequest | N
538 | 02-CPR-DTG Model Modeler Work Test 7 | 2 - CommercialPartRequest | N
539 | 02-CPR-DTG Model Modeler Work Test 8 | 2 - CommercialPartRequest | N
540 | 02-CPR-DTG Model Modeler Work Test 9 | 2 - CommercialPartRequest | N
541 | 02-CPR-DTG Model Modeler Work Test 10 | 2 - CommercialPartRequest
542 | 02-CPR-TAG Model Create Request Test 9 | 2 - CommercialPartRequest | N
543 | 02-CPR-TAG Model Create Request Test 10 | 2 - CommercialPartRequest | N
544 | 02-CPR-TAG Model Create Request Test 11 | 2 - CommercialPartRequest | N
545 | 02-CPR-TAG Model Create Request Test 12 | 2 - CommercialPartRequest | N
547 | 02-CPR-TAG Model Create Request Test 1 | 2 - CommercialPartRequest | N
548 | 02-CPR-TAG Model Create Request Test 2 | 2 - CommercialPartRequest | N
549 | 02-CPR-TAG Model Create Request Test 3 | 2 - CommercialPartRequest | N
550 | 02-CPR-TAG Model Create Request Test 4 | 2 - CommercialPartRequest | N
551 | 02-CPR-TAG Model Create Request Test 5 | 2 - CommercialPartRequest | N
552 | 02-CPR-TAG Model Create Request Test 6 | 2 - CommercialPartRequest | N
553 | 02-CPR-TAG Model Create Request Test 7 | 2 - CommercialPartRequest | N
554 | 02-CPR-TAG Model Create Request Test 8 | 2 - CommercialPartRequest
555 | 02-CPR-TAG Model wf Test 1 | 2 - CommercialPartRequest | N | Medium (5)
556 | 02-CPR-TAG Model wf Test 2 | 2 - CommercialPartRequest | N
557 | 02-CPR-TAG Model wf Test 3 | 2 - CommercialPartRequest | N
558 | 02-CPR-TAG Model wf Test 4 | 2 - CommercialPartRequest | N
559 | 02-CPR-TAG Model wf Test 5 | 2 - CommercialPartRequest | N
560 | 02-CPR-TAG Model wf Test 6 | 2 - CommercialPartRequest | N
561 | 02-CPR-TAG Model wf Test 7 | 2 - CommercialPartRequest | Y |  | Complete |  | January 31 | Rhey | DONE
562 | 02-CPR-TAG Model wf Test 8 | 2 - CommercialPartRequest | N
563 | 02-CPR-TAG Model wf Test 9 | 2 - CommercialPartRequest | N
564 | 02-CPR-TAG Model wf Test 10 | 2 - CommercialPartRequest | N
565 | 02-CPR-TAG Model wf Test 11 | 2 - CommercialPartRequest | N
566 | 02-CPR-TAG Model wf Test 12 | 2 - CommercialPartRequest | N
567 | 02-CPR-TAG Model Modeler Work Test 1 | 2 - CommercialPartRequest | N
568 | 02-CPR-TAG Model Modeler Work Test 2 | 2 - CommercialPartRequest | N
569 | 02-CPR-TAG Model Modeler Work Test 3 | 2 - CommercialPartRequest | N
570 | 02-CPR-TAG Model Modeler Work Test 4 | 2 - CommercialPartRequest | N
571 | 02-CPR-TAG Model Modeler Work Test 5 | 2 - CommercialPartRequest | N
572 | 02-CPR-TAG Model Modeler Work Test 6 | 2 - CommercialPartRequest | N
573 | 02-CPR-TAG Model Modeler Work Test 7 | 2 - CommercialPartRequest | N
574 | 02-CPR-TAG Model Modeler Work Test 8 | 2 - CommercialPartRequest | N
575 | 02-CPR-TAG Model Modeler Work Test 9 | 2 - CommercialPartRequest | N
576 | 02-CPR-TAG Model Modeler Work Test 10 | 2 - CommercialPartRequest
577 | CAE - Admin needs to change part data for a Released PCBA Part | 4 - DisciplineSpecificEdit | Y |  |  |  | April 30
578 | CAE - Admin needs to change part data for a Released Part to Lift Eng Control Flag | 4 - DisciplineSpecificEdit | Y |  |  |  | April 30
579 | CAE - Admin needs to change part data for a Part that is not Released | 4 - DisciplineSpecificEdit | Y | High (10) |  |  | April 30
580 | CAE - Admin needs to change part data for an Electro-Mech Part that is related to an ECN | 4 - DisciplineSpecificEdit | Y |  |  |  | April 30
581 | CAE - Someone other Business Admin needs to change part data | 4 - DisciplineSpecificEdit | Y |  |  |  | April 30
582 | CAE - Admin needs to change part data for a down rev'd part | 4 - DisciplineSpecificEdit | Y |  |  |  | April 30
583 | DFM Group member needs to change Part data for a Released Divisional Part | 4 - DisciplineSpecificEdit | N
584 | DFM Group Member needs to change Part data for a Released Commercial Part | 4 - DisciplineSpecificEdit | N
585 | DFM Group Member needs to change Part data for a Part that is not Released | 4 - DisciplineSpecificEdit | N
586 | DFM Group Member needs to change Part data for a Part that is related to an ECN | 4 - DisciplineSpecificEdit | N
587 | DFM - Someone not in the DFM Group needs to change Part data for a Part | 4 - DisciplineSpecificEdit | N
588 | DFM - Someone in the DFM Group needs to change Part data for a down rev'd Part | 4 - DisciplineSpecificEdit | Y |  |  |  | April 30
589 | Reliability Group member needs to Change Part data for a Commercial Part | 4 - DisciplineSpecificEdit | Y |  |  |  | April 30
590 | Reliability Group member needs to Change Part data for a Divisional Part | 4 - DisciplineSpecificEdit | Y |  |  |  | April 30
591 | Someone other than Reliability Group member needs to Change Part data for a Part | 4 - DisciplineSpecificEdit | N
592 | Insure Part Change History is required | 4 - DisciplineSpecificEdit | Y |  |  |  | April 30
593 | Safety Group member needs to Change Part data for a Released Part | 4 - DisciplineSpecificEdit | Y |  |  |  | April 30
594 | Safety Group member needs to Change Part data for a Commercial Part | 4 - DisciplineSpecificEdit | Y |  |  |  | April 30
595 | Safety Group member needs to Change Part data for a Part that is not Released | 4 - DisciplineSpecificEdit | Y |  |  |  | April 30
596 | Safety Group member needs to Change Part data for a Part that is related to an ECN | 4 - DisciplineSpecificEdit | Y |  |  |  | April 30
597 | Someone other than Safety Group member needs to Change Part data for a Part that is not Released | 4 - DisciplineSpecificEdit | N
598 | A Safety Group member needs to Change Part data for a down rev'd Part | 4 - DisciplineSpecificEdit | N
599 | SBM Engineer needs to Change Part data for a Released Part | 4 - DisciplineSpecificEdit | Y |  |  |  | April 30
600 | SBM Engineer needs to Change Part data for a Commercial Part | 4 - DisciplineSpecificEdit | Y | High (10) |  |  | April 30
601 | SBM Engineer needs to Change Part data for a Part that is not Released | 4 - DisciplineSpecificEdit | N | High (10)
602 | SBM Engineer needs to Change Part data for a Part that is related to an ECN | 4 - DisciplineSpecificEdit | Y |  |  |  | April 30
603 | Someone other than SBM Engineer needs to Change Part data for a Part | 4 - DisciplineSpecificEdit | Y |  |  |  | April 30
604 | An SBM Engineer needs to Change Part data for a down rev'd Part | 4 - DisciplineSpecificEdit | N
605 | A member of the Compliance Edits group needs to add-change ECCN and or HTS Codes for a Released Part | 4 - DisciplineSpecificEdit | Y | High (10) |  |  | April 30
606 | Trade Compliance member needs to add-change ECCN and or HTS Codes for a Commercial Part | 4 - DisciplineSpecificEdit | Y | High (10) |  |  | April 30
607 | Trade Compliance member needs to add-change ECCN and or HTS Codes for a Part that is not Released | 4 - DisciplineSpecificEdit | Y |  |  |  | April 30
608 | Trade Compliance member needs to add-change ECCN and or HTS Codes for a Part that is related to an ECN | 4 - DisciplineSpecificEdit | Y | High (10) |  |  | April 30
609 | Trade Compliance member needs to add-change ECCN and or HTS Codes for a Part where the codes are invalid in Oracle | 4 - DisciplineSpecificEdit | Y |  |  |  | April 30
610 | Someone other than Trade Compliance member needs to add-change ECCN and or HTS Codes for any Part | 4 - DisciplineSpecificEdit | N
611 | Trade Compliance member needs to make a change to a down rev'd part | 4 - DisciplineSpecificEdit | N
612 | 3-PM-Part Modification Request Test 1 | 3 - PartModification | Y | Low (2) |  |  | April 30
613 | 3-PM-Part Modification Request Test 2 | 3 - PartModification | Y | Low (2) |  |  | April 30
614 | 3-PM-Part Modification Request Test 3 | 3 - PartModification | N | Low (2)
615 | 3-PM-Part Modification Request Test 4 | 3 - PartModification | N
616 | 3-PM-Part Modification Request Test 5 | 3 - PartModification | N
617 | 3-PM-Part Modification Request Test 6 | 3 - PartModification | N
618 | 3-PM-Part Modification Request Test 7 | 3 - PartModification | N
619 | 3-PM-Part Modification Request Test 8 | 3 - PartModification | N
620 | 3-PM-Part Modification Request Test 9 | 3 - PartModification | N | Low (2)
621 | 3-PM-Part Modification Request Test 10 | 3 - PartModification | N
622 | 3-PM-Part Modification Request Test 11 | 3 - PartModification | N
624 | 3-PM-Part Modification Request Test 13 | 3 - PartModification | N
625 | 3-PM-Part Modification Request Test 14 | 3 - PartModification | N
626 | 3-PM-Part Modification Request Test 15 | 3 - PartModification | N
627 | 3-PM-Part Modification Request Test 16 | 3 - PartModification | N
628 | 3-PM-Part Modification Request Test 17 | 3 - PartModification | N | Low (2)
629 | 3-PM-Part Modification Request Test 18 | 3 - PartModification | N
630 | 3-PM-Part Modification Workflow Test 1 | 3 - PartModification | N
631 | 3-PM-Part Modification Workflow Test 2 | 3 - PartModification | N
632 | 3-PM-Part Modification Workflow Test 3 | 3 - PartModification | N
633 | 3-PM-Part Modification Workflow Test 4 | 3 - PartModification
634 | 3-PM-Part Modification Workflow Test 5 | 3 - PartModification | N
635 | 3-PM-Part Modification Workflow Test 6 | 3 - PartModification | N
636 | 3-PM-Part Modification Workflow Test 7 | 3 - PartModification
637 | 3-PM-Part Modification Workflow Test 8 | 3 - PartModification
638 | 3-PM-Part Modification Workflow Test 9 | 3 - PartModification | N
639 | 3-PM-Part Modification Workflow Test 10 | 3 - PartModification | Y |  |  |  | April 30
640 | 3-PM-Part Modification Workflow Test 11 | 3 - PartModification | N
641 | 3-PM-Part Modification Workflow Test 12 | 3 - PartModification | N
642 | 3-PM-Part Modification Workflow Test 13 | 3 - PartModification | N
643 | 3-PM-Part Modification Workflow Test 14 | 3 - PartModification |  | Low (2)
644 | 3-PM-Part Modification Workflow Test 15 | 3 - PartModification | N
645 | 3-PM-Part Modification Workflow Test 16 | 3 - PartModification | N
646 | 3-PM-Part Modification Workflow Test 17 | 3 - PartModification
647 | 3-PM-Part Modification Workflow Test 18 | 3 - PartModification | Y |  |  |  | April 30
649 | 13-CE-Create Commodity Level 1 Form Test 2 | 13 - CommEnggTransfer | Y |  |  |  | April 30
650 | 13-CE-Make Change to Commodity Level 1 Form Test 1 | 13 - CommEnggTransfer | N | Low (2)
651 | 13-CE-Make Change to Commodity Level 1 Form Test 2 | 13 - CommEnggTransfer | Y |  |  |  | April 30
655 | 13-CE- Commodity Engineer Transfer Request Workflow Test 2 | 13 - CommEnggTransfer | Y |  |  |  | April 30
657 | Re-classify a Vendor | 17 - SupplierRating
659 | 18-VM-Cut Dataset Test 1 | 18 - VendorManagement | N | Low (2)
660 | 18-VM-Cut Dataset Test 2 | 18 - VendorManagement | N
661 | 18-VM-Cut Dataset Test 3 | 18 - VendorManagement | N
663 | 18-VM-Cut Dataset Test 5 | 18 - VendorManagement | N
665 | 18-VM-Cut Dataset Test 8 | 18 - VendorManagement | N
666 | 18-VM-Cut Dataset Test 9 | 18 - VendorManagement | N
669 | 18-VM-Cut Dataset Test 13 | 18 - VendorManagement | N
670 | 18-VM-Cut Dataset Test 14 | 18 - VendorManagement | N
673 | 18-VM-Delete Dataset Test 3 | 18 - VendorManagement | N | Low (2)
675 | 18-VM-Delete Dataset Test 5 | 18 - VendorManagement | N
676 | 18-VM-Delete Dataset Test 7 | 18 - VendorManagement | N
677 | 18-VM-Delete Dataset Test 8 | 18 - VendorManagement | N
678 | 18-VM-Delete Dataset Test 9 | 18 - VendorManagement | N
679 | 18-VM-Delete Dataset Test 10 | 18 - VendorManagement | N
680 | 18-VM-Delete Dataset Test 11 | 18 - VendorManagement | N
682 | 18-VM-Relate Dataset to Part Test 2 | 18 - VendorManagement | N
683 | 18-VM-Relate Dataset to Part Test 3 | 18 - VendorManagement | N
686 | 18-VM-Relate Dataset to Part Test 7 | 18 - VendorManagement | N
687 | 18-VM-Relate Dataset to Part Test 8 | 18 - VendorManagement | N
688 | 18-VM-Relate Dataset to Part Test 9 | 18 - VendorManagement | N
689 | 18-VM-Relate Dataset to Part Test 10 | 18 - VendorManagement | N
690 | 18-VM-Drag and Drop Dataset to Part Test 1 | 18 - VendorManagement | N
691 | 18-VM-Drag and Drop Dataset to Part Test 2 | 18 - VendorManagement | N
692 | 18-VM-Drag and Drop Dataset to Part Test 3 | 18 - VendorManagement | N
693 | 18-VM-Drag and Drop Dataset to Part Test 4 | 18 - VendorManagement | N
694 | 18-VM-Drag and Drop Dataset to Part Test 5 | 18 - VendorManagement | N
695 | 18-VM-Drag and Drop Dataset to Part Test 7 | 18 - VendorManagement | N
696 | 18-VM-Drag and Drop Dataset to Part Test 8 | 18 - VendorManagement | N
697 | 18-VM-Drag and Drop Dataset to Part Test 9 | 18 - VendorManagement | N
698 | 18-VM-Drag and Drop Dataset to Part Test 10 | 18 - VendorManagement | N
699 | 18-VM-Vendor Part Creation Test 1 | 18 - VendorManagement | N | Low (2)
700 | 18-VM-Vendor Part Creation Test 2 | 18 - VendorManagement
701 | 18-VM-Vendor Part Creation Test 3 | 18 - VendorManagement | N
702 | 18-VM-Vendor Part Creation Test 4 | 18 - VendorManagement | N
704 | 18-VM-Vendor Part Creation Test 6 | 18 - VendorManagement | N | Low (2)
705 | 18-VM-Vendor Part Creation Test 10 | 18 - VendorManagement | N
708 | 18-VM-Vendor Part Creation Test 15 | 18 - VendorManagement | N
709 | 18-VM-Vendor Part Creation Test 16 | 18 - VendorManagement | N
710 | 18-VM-Vendor Part Creation Test 17 | 18 - VendorManagement | N
712 | 18-VM-Vendor Part Modify Test 1 | 18 - VendorManagement
713 | 18-VM-Vendor Part Modify Test 2 | 18 - VendorManagement | Y |  |  |  | April 30
714 | 18-VM-Vendor Part Modify Test 3 | 18 - VendorManagement | N
715 | 18-VM-Vendor Part Modify Test 4 | 18 - VendorManagement | N
718 | 18-VM-Vendor Part Modify Test 7 | 18 - VendorManagement | N
719 | 18-VM-Vendor Part Modify Test 8 | 18 - VendorManagement | N
720 | 18-VM-Vendor Part Modify Test 9 | 18 - VendorManagement | N
721 | 18-VM-Vendor Part Modify Test 10 | 18 - VendorManagement | N
722 | 18-VM-Vendor Part Modify Test 11 | 18 - VendorManagement | N
723 | 18-VM-Vendor Part Modify Test 12 | 18 - VendorManagement | N
725 | 18-VM-Vendor Part Modify Test 14 | 18 - VendorManagement | N
727 | 18-VM-Vendor Part Modify Test 16 | 18 - VendorManagement | N
728 | 18-VM-Vendor Part Modify Test 17 | 18 - VendorManagement | N
729 | 18-VM-Vendor Part Modify Test 18 | 18 - VendorManagement | N
730 | 18-VM-Vendor Part Modify Test 19 | 18 - VendorManagement | N
731 | 18-VM-Vendor Part Modify Test 20 | 18 - VendorManagement | N
732 | 18-VM-Copy and Paste Dataset to Part, Test 1 | 18 - VendorManagement | N
733 | 18-VM-Copy and Paste Dataset to Part, Test 2 | 18 - VendorManagement | N
734 | Create a new Project Form | 21 - AdminEditor | Y |  |  |  | May 31
735 | Create a new Project Form as someone other than Business Change Admin | 21 - AdminEditor | Y |  |  |  | May 31
736 | Create a new Project Form where one or more people do not have an account | 21 - AdminEditor | Y |  |  |  | May 31
737 | 21-Edit a Project Form Test 1 | 21 - AdminEditor | Y |  |  |  | May 31
738 | 21-Edit a Project Form that is releated to an unreleased part | 21 - AdminEditor | Y |  |  |  | May 31
739 | 21-Edit a Project Form that is releated to an open ECN | 21 - AdminEditor | Y |  |  |  | May 31
740 | 21-Edit a Project Form as someone other than Business Change Admin | 21 - AdminEditor | Y |  |  |  | May 31
741 | 21-Edit a Project Form one or more people do not have accounts | 21 - AdminEditor | Y |  |  |  | May 31
742 | Exclude projects from being displayed in LOVs Test | 21 - AdminEditor | Y |  |  |  | May 31
743 | Exclude projects that is related to an ECN from being displayed in Drop Down Lists | 21 - AdminEditor | Y |  |  |  | May 31
744 | Testing Roles and Groups Test 1 | 22 - Security | N
745 | 6-REL-ECN Sign Off Tab-Test 1 | 6 - ReleaseECN | Y |  |  |  | January 31 | Rodji | DONE
746 | 7-PB-ECN Sign Off Tab-Test 1 | 7 - ProtoBOMECN | Y |  |  |  | February 28 | Marjorie | DONE |  | YES | ECN031134 as an example on the screenshot on the test case is not a ProtoBOM ECN, but a Release ECN; used ECN050087 instead, please see below picture
747 | 9-PCN-Sign Off Tab-Test 1 | 9 - PCN | Y |  |  |  | May 31
748 | 01-Div Part- Planner Assigns new Oracle Org to exisiting Assembly Part-Test 4 | 1 - DivisionalPartRequest | Y | High (10) | Complete | January 27 | January 31 | Marjorie | DONE
749 | 5-CHG-Std ECN for Div Parts-10 | 5 - ChangeECN | N
750 | 14-SC-Calculation on BOMS & Reports View | 14 - SubstanceCompliance | Y | High (10) |  |  | April 30
752 | 26-SS-Validate Help Screens | 26 - 227081 Solution Specification - Migration_r05* | Y |  |  |  | April 30
753 | 26-SS-Change or Update Help Screens | 26 - 227081 Solution Specification - Migration_r05* | Y |  |  |  | April 30
754 | 5-CHG-Std ECN for Div Parts-Test 11 | 5 - ChangeECN | N
755 | 01-Div Part- Planner Assigns new Oracle Org to exisiting Assembly Part-Test 5 | 1 - DivisionalPartRequest | Y |  | Complete |  | January 31 | Marjorie | DONE |  | YES | Used Part Number 654-949-00 instead of 601-355-05
756 | 5-CHG-Std ECN for Div Parts-Test 12 | 5 - ChangeECN | Y |  |  |  | February 28 | Marjorie | DONE
757 | 36 - Upload a new BOM on a new part with no find numbers | 36 - BOMImportEdit | Y | Medium (5) |  |  | March 31
758 | 36 - Upload a new BOM on a new part with find numbers | 36 - BOMImportEdit | Y | Medium (5) |  |  | March 31
759 | 36 - Upload an Expanded BOM | 36 - BOMImportEdit | Y | Medium (5) |  |  | March 31
760 | 36 -Upload a BOM without refdes | 36 - BOMImportEdit | Y | Medium (5) |  |  | March 31
761 | 36 -Upload a BOM to a Non-Working part | 36 - BOMImportEdit | N
762 | 36 - Upload a BOM with a bad child | 36 - BOMImportEdit | N
763 | 36 -Upload a BOM with a quantity less than the number of refdes | 36 - BOMImportEdit | N
764 | 36 -Upload a BOM with a quantity greater than the number of refdes | 36 - BOMImportEdit | N
765 | 36 - Upload a BOM with missing assembly | 36 - BOMImportEdit | N
766 | 36 - Upload a BOM with bad header field name | 36 - BOMImportEdit | N
767 | 36 - Upload a BOM with bad header format - lower case | 36 - BOMImportEdit | N
768 | 36 - Upload a BOM with a bad item format | 36 - BOMImportEdit | N
770 | 36 - Upload a BOM into a Commodity Part | 36 - BOMImportEdit | N
771 | 36 - Upload a BOM into an assembly where the assembly is listed in the BOM - Circular reference | 36 - BOMImportEdit | N
772 | 36 - Upload a BOM with some quantity of REFDES and additional parts without refdes | 36 - BOMImportEdit | N
773 | 36 - Upload a non-CSV BOM | 36 - BOMImportEdit | N
774 | 36 - Upload a BOM with missing commas | 36 - BOMImportEdit | N
775 | 36 - Upload a BOM with extra commas | 36 - BOMImportEdit | N
776 | 36 - Upload a BOM with extra header field | 36 - BOMImportEdit | N
777 | 36 - Upload a BOM with zero quantity item | 36 - BOMImportEdit | N
778 | 36 - Upload a packed BOM similar to existing PCBA BOM | 36 - BOMImportEdit | N
779 | 36 - Upload a flat BOM similar to existing PCBA BOM | 36 - BOMImportEdit | N
780 | 36 - Upload a BOM where components are not listed in order | 36 - BOMImportEdit | N
781 | 36 - Verify ranging in packed view | 36 - BOMImportEdit | N | Medium (5)
782 | 36 - Verify ranging in packed view with Alpha refdes | 36 - BOMImportEdit | N
783 | 36 - Verify refdes ordering | 36 - BOMImportEdit | N
784 | 36 - Spaces in cells trim and acceptable options | 36 - BOMImportEdit | N
785 | 36 - Upload BOM with duplicate refdes | 36 - BOMImportEdit | N | Medium (5)
786 | 36 -Upload BOM to an assembly checked out by another user | 36 - BOMImportEdit | Y |  |  |  | March 31
787 | 36 -Upload BOM to an assembly checked out by same user | 36 - BOMImportEdit | Y |  |  |  | March 31
788 | 36 - Multiple assemblies in BOM | 36 - BOMImportEdit | Y |  |  |  | March 31
790 | 36 - Load a large flat PCBA BOM | 36 - BOMImportEdit | Y | Medium (5) |  |  | March 31
791 | 36 - Load a large packed PCBA BOM | 36 - BOMImportEdit | Y | Medium (5) |  |  | March 31
792 | 36 - Update a BOM with quantity not less than ref des | 36 - BOMImportEdit | N
794 | 36 - Load an empty BOM | 36 - BOMImportEdit | N
795 | 36 - Edit BOM lines when quantity and refdes are same | 36 - BOMImportEdit | Y | Medium (5) |  |  | March 31
796 | 36 - Edit BOM lines when quantity has data and refdes is empty | 36 - BOMImportEdit | N | Medium (5)
797 | 36 - Edit BOM lines by copy and pasting from excel | 36 - BOMImportEdit | Y | Medium (5) |  |  | March 31
798 | 36 - Edit BOM lines so quantity is less than refdes | 36 - BOMImportEdit | N
799 | 36 - Edit BOM lines so quantity is more than refdes | 36 - BOMImportEdit | N
800 | 26-Carolyn_DM Test _Project Forms | 26 - 227081 Solution Specification - Migration_r05* | Y | High (10) |  |  | April 30
801 | 26-Carolyn_DM Test _ProtoBOM ECN | 26 - 227081 Solution Specification - Migration_r05* | Y |  |  |  | April 30
802 | 26-Carolyn_DM Test _Release ECN | 26 - 227081 Solution Specification - Migration_r05* | Y | High (10) |  |  | April 30
803 | 26-Carolyn_DM Test _Release ECN | 26 - 227081 Solution Specification - Migration_r05* | Y | High (10) |  |  | April 30
804 | 26-Carolyn_DM Test _Standard ECN | 26 - 227081 Solution Specification - Migration_r05* | Y |  |  |  | April 30
805 | 26-Carolyn_DM Test_BOM | 26 - 227081 Solution Specification - Migration_r05* | Y | High (10) |  |  | April 30
806 | 26-Carolyn_DM Test_Div Parts | 26 - 227081 Solution Specification - Migration_r05* | Y |  |  |  | April 30
807 | 26-Cindy_DM Test_Design | 26 - 227081 Solution Specification - Migration_r05* | Y |  |  |  | April 30
808 | 26-Cindy_DM Test_ECO | 26 - 227081 Solution Specification - Migration_r05* | Y |  |  |  | April 30
809 | 26-Cindy_DM Test_GenDocs | 26 - 227081 Solution Specification - Migration_r05* | Y | High (10) |  |  | April 30
810 | 26-Peter_ DM Device Package | 26 - 227081 Solution Specification - Migration_r05* | Y |  |  |  | April 30
811 | 26-Peter_DM_Comm. Eng. Transfer | 26 - 227081 Solution Specification - Migration_r05* | Y |  |  |  | April 30
812 | 26-Peter_DM_CommodityPartRequest | 26 - 227081 Solution Specification - Migration_r05* | Y |  |  |  | April 30
813 | 26-Peter_DM Discontinuance | 26 - 227081 Solution Specification - Migration_r05* | Y |  |  |  | April 30
814 | 26-Peter_DM DTGmdl Modify | 26 - 227081 Solution Specification - Migration_r05* | Y | High (10) |  |  | April 30
815 | 26-Peter_DM Part Modify | 26 - 227081 Solution Specification - Migration_r05* | Y |  |  |  | April 30
816 | 26-Peter_DM Supplier Transfer | 26 - 227081 Solution Specification - Migration_r05* | Y |  |  |  | April 30
817 | 26-Peter_DM TAGmdl Create | 26 - 227081 Solution Specification - Migration_r05* | Y |  |  |  | April 30
818 | 26-Peter_DM TAGmdl Modify | 26 - 227081 Solution Specification - Migration_r05* | Y |  |  |  | April 30
819 | 26-Peter_DM Vendor Part | 26 - 227081 Solution Specification - Migration_r05* | Y | High (10) |  |  | April 30
820 | 32-SR-Login Test Script for Performance-First time login | 32 - Support Reports | Y |  |  |  | May 31
821 | 32-SR-Login Test Script for Performance-second time+ login | 32 - Support Reports | N
822 | 32-SR-Login Test Script for Performance-AWC login | 32 - Support Reports | Y |  |  |  | May 31
823 | 5-CHG-Std ECN Re-Issue-Test 1 | 5 - ChangeECN | Y | Medium (5) |  |  | February 28 | Marjorie | DONE
824 | 28-Upload a BOM with quantity greater than zero and no refdes | 28 - NPI BOM Loader | Y | High (10) |  |  | March 31
825 | 5-CHG-Std ECN Re-Issue-Test 2 | 5 - ChangeECN | Y |  |  |  | February 28 | Marjorie | DONE
827 | 5-CHG-STD ECN to Revise Legacy revisions for Assemblies and components. | 5 - ChangeECN | Y | High (10) |  |  | February 28 | Marjorie |  | 16
828 | Fallout Report testing | 26 - 227081 Solution Specification - Migration_r05* | Y | High (10) |  |  | April 30
829 | 16-RPT-QUICK COMPARE | 16 - SearchAndReports | Y | Medium (5) |  |  | March 31
832 | 26-Peter_DM Substance Compliance | 26 - 227081 Solution Specification - Migration_r05* | Y |  |  |  | April 30
833 | 26-Mike_DM PCN | 26 - 227081 Solution Specification - Migration_r05* | Y | High (10) |  |  | April 30
834 | 28-Working version checked out by other user | 28 - NPI BOM Loader | Y |  |  |  | March 31
835 | 28-Working version checked out by same user | 28 - NPI BOM Loader | Y |  |  |  | March 31
836 | 28-Upload a BOM using the email results function | 28 - NPI BOM Loader | Y | High (10) |  |  | March 31
837 | 01-New Div Part - PO star to A | 1 - DivisionalPartRequest | Y | High (10) | Oracle |  | January 31 | Marjorie | NA |  |  | Test case in Oracle
838 | 36-BOM Upload Fix Redo File | 36 - BOMImportEdit | Y | Medium (5) |  |  | March 31
839 | 9-PCN-Manual workflow to close Open PCNs migrated in from Enterprise | 9 - PCN | Y | High (10) |  |  | May 31
840 | 26-DM-LOV | 26 - 227081 Solution Specification - Migration_r05* | Y | High (10) |  |  | April 30
841 | 01-Div Part- Planner Assigns new Oracle Org to exisiting Assembly Part-Test 6 | 1 - DivisionalPartRequest | Y | Medium (5) | Complete |  | January 31 | Marjorie | DONE
842 | 5-CHG-Std ECN for Div Part with BOM-Test 12 | 5 - ChangeECN | Y | High (10) |  |  | February 28 | Marjorie |  | 16
843 | 5-CHG-Std ECN for Div Part with BOM-Test 15 | 5 - ChangeECN | Y | High (10) |  |  | February 28 | Marjorie |  | 8
844 | Oracle_InterfaceTable | 31 - Interface + Feeds | N | Medium (5)
845 | 31-Compare Unified AML feed and Enterprise AML feed | 31 - Interface + Feeds | N | Low (2)
846 | 31-Compare Unified ORULE feed and Enterprise ORULE feed | 31 - Interface + Feeds | Y | Low (2) |  |  | May 31
847 | 31-Compare Unified OPART feed and Enterprise OPART feed | 31 - Interface + Feeds | Y | Low (2) |  |  | May 31
848 | 01-Div Part-PO rev star to A testing | 1 - DivisionalPartRequest | Y | Low (2) | Oracle |  | January 31 | Marjorie | NA |  |  | Test case in Oracle
849 | Edge Case Testing- Various file types | 26 - 227081 Solution Specification - Migration_r05* | Y | Low (2) |  |  | April 30
850 | IT - Helpdesk support process | 33 - Support Processes | Y | Low (2) |  |  | May 31
851 | 16-SER-Subscribe to a selected object | 16 - SearchAndReports | Y | Medium (5) |  |  | March 31
852 | 16-SER-subscribe to an object class | 16 - SearchAndReports | Y | Low (2) |  |  | March 31
853 | 16-SER-Manage Subscriptions | 16 - SearchAndReports | Y | Low (2) |  |  | March 31
854 | 5-CHG-Reviewers Matrix | 5 - ChangeECN | Y | Low (2) |  |  | February 28 | Marjorie | DONE |  | YES | Can view the link by opening IE, not by clicking the link in TeamCenter
855 | 01-Div Part- Planner Assigns a new Oracle Org to exisiting CB1 | 1 - DivisionalPartRequest | Y | Low (2) | Complete |  | January 31 | Marjorie | DONE
856 | 23 - DOC CONTROL -REVISE DOCUMENT WITHOUT ECN | 23 - DocumentManagement | N | Low (2)
857 | 5-CHG-Std ECN FOR PERFORMANCE TEST | 5 - ChangeECN | Y | Low (2) |  |  | February 28 | Marjorie |  | 8
858 | 16-SER and RPT-ShipRev | 16 - SearchAndReports | N | Low (2)
859 | 5-CHG-Do Now ECN | 5 - ChangeECN | N | Low (2)
860 | 01-Div Part - Admin needs to release parts outside of ECN process | 1 - DivisionalPartRequest | Y | Low (2) | Complete |  | January 31 | Marjorie | DONE
861 | 31-MiniSmokeTest | 31 - Interface + Feeds | Y | Low (2) |  |  | May 31
862 | 5-CHG-Std ECN Set Out of Office for Absent User | 5 - ChangeECN | Y | Low (2) |  |  | February 28 | Marjorie | DONE
863 | 5-CHG - ECN Rejected while tech review User is Out of Office | 5 - ChangeECN | Y | Low (2) |  |  | February 28 | Marjorie | DONE |  | YES | Failed on step 8. Workaround: tried login as dba(mishraan), set the assigned party to mishraan(dba) and set the User-Group/Role to surrogate(adlerky)
864 | 29-PLS-Part List Search - Duplicate Parts | 29 - Part List Search (PLS) | N | Low (2)
865 | 35-PST-Duplicate Parts | 30 - TcRA Reports | N | Low (2)
866 | 32-ECNIncorpReport | 32 - Support Reports | Y | Low (2) |  |  | May 31
867 | 32-Defaulters List Report | 32 - Support Reports | Y | Low (2) |  |  | May 31
868 | 32-ECN Metrics Report | 32 - Support Reports | Y | Low (2) |  |  | May 31
869 | 16-Where Used - error while finding components | 16 - SearchAndReports | N | Low (2)
870 | 23-DP-Baseline a Device Package (4) | 23 - DocumentManagement |  | Low (2)
871 | 5-CHG-Check out certain object types during review or executing | 5 - ChangeECN | Y | Low (2) |  |  | February 28 | Marjorie |  | 16
872 | 36 - BOMImport with QTY NULL-Test 45 | 36 - BOMImportEdit | Y | Low (2) |  |  | March 31
873 | 36 - Structure manager QTY NULL-Test 46 | 36 - BOMImportEdit | Y | Low (2) |  |  | March 31
874 | 10-ECN SUMMARY Notice proto to prod-Test 9 | 10 - ECNSummaryReport | Y | Low (2) |  |  | February 28 | Marjorie | DONE
875 | 36-Item Status on BOM Structure Manager | 36 - BOMImportEdit | Y | Medium (5) |  |  | March 31
876 | 10-ECNSummaryReport ProcessHistory Sort | 10 - ECNSummaryReport | Y | Low (2) |  |  | February 28 | Marjorie | DONE
877 | 23-DocMgt-Drag and Drop Visio file | 23 - DocumentManagement | Y | Medium (5) |  |  | May 31
878 | 2-CommPart-AVL tab display | 2 - CommercialPartRequest |  | Medium (5)
879 | 5-CHG-Add a File to an Open ECN-Test 1 | 5 - ChangeECN | Y | Medium (5) |  |  | February 28 | Marjorie | DONE |  | YES | Cannot add file to Files folder but can add to ECN revision, it will throw an error "The relationship of type 'Files' is not supported between of types 'Standard ECN Revision' and 'WorkspaceObject'"(Test Case 1 failed)
880 | 5-CHG-Check out certain object types after ECN is resubmitted to review or executing | 10 - ECNSummaryReport | Y | High (10) |  |  | February 28 | Marjorie | In Progress | 8
881 | 16-SER- TER All Parts Search | 16 - SearchAndReports |  | Low (2)
882 | 5-CHG-Expidite Reject and reapproval | 5 - ChangeECN |  | High (10)
883 | 5-CHG-Revising migrated parts with special revisions | 5 - ChangeECN |  | Low (2)
884 | 10-ECNSummaryReport-decimals in BOM | 10 - ECNSummaryReport | Y | Medium (5) |  |  | February 28 | Marjorie | In Progress | 8
885 | 32-SR-Generate BOM Reports | 32 - Support Reports |  | Low (2)
886 | 2-Comm Part-Classification Search Properties | 2 - CommercialPartRequest |  | Low (2)
887 | 33-SP-Help Menu Links | 33 - Support Processes |  | Low (2)
888 | 5-CHG-ECN Emails | 5 - ChangeECN | Y | Medium (5) |  |  | February 28 | Marjorie |  | 16
889 | 35-PST-AVL Search Results | 35 - Part Selection Tool (PST) |  | Low (2)
890 | 10-ECN Summary Report Links | 10 - ECNSummaryReport |  | Low (2)
891 | 33-SP-Splash Screen | 33 - Support Processes | Y | Low (2) |  |  | May 31
892 | 14-SC-Manually Invoking RoHS Compliancy Status Recalculation-Test 3 | 14 - SubstanceCompliance |  | Medium (5)
893 | 1-Div Part-ECN Change History Tab | 1 - DivisionalPartRequest | Y | Medium (5) | Complete |  | January 31 | Marjorie | DONE
894 | 23-DocMgt-Drag and Drop files | 23 - DocumentManagement | Y | High (10) |  |  | May 31
895 | 5-CHG-ECN Folder Structure | 5 - ChangeECN |  | Low (2)
896 | 5-CHG-ECN task color coding | 5 - ChangeECN |  | Low (2)
897 | 5-CHG-Std ECN Expedite Approve or Reject-Test 5 | 5 - ChangeECN | Y | High (10) |  |  | February 28 | Marjorie | DONE |  | YES | The screenshot on Test case did not show the expedite sign off
898 | 2-CommPart-AVL Preferred Status | 2 - CommercialPartRequest | Y | Low (2) | Complete |  | January 31 | Rhey | DONE
899 | 9-PCN-Create PCN-Test 4 | 9 - PCN | Y | High (10) |  |  | May 31
900 | 10-ECN Summary Reports - Test 1 | 10 - ECNSummaryReport | Y | Medium (5) |  |  | February 28 | Marjorie |  | 4 | YES | empty Doc1 Release ECN and Doc2 Release ECN, please see below picture
901 | 26-DM-Prototype Asterisk Revision Parts | 26 - 227081 Solution Specification - Migration_r05* |  | Low (2)
902 | 2-CommPart-Access to Edit Part | 2 - CommercialPartRequest | Y | High (10) | Complete | January 27 | January 31 | Rhey | DONE
903 | 2-CPR-Commercial Part Request Create Form | 2 - CommercialPartRequest | Y | Low (2) | Complete |  | January 31 | Rhey | DONE
904 | 2-Req-Request Create Forms | 2 - CommercialPartRequest | Y | Low (2) | Complete |  | January 31 | Rhey | DONE
906 | 5-CHG-Email Notify for reassigned task | 5 - ChangeECN |  | Low (2)
907 | 16-SR- Future Effective ECN Report | 16 - SearchAndReports |  | Low (2)
908 | 6-RelECN-Release Legacy Part Revision that have one sequence that are locked | 6 - ReleaseECN |  | Low (2)
909 | 4-DSE-UI DFM Attributes parts not refreshing quickly based on compliance changes | 4 - DisciplineSpecificEdit |  | Low (2)
910 | 3-PM-Part Modify Request email comments field | 3 - PartModification |  | Low (2)
911 | 3-PM-Report for tracking Part Modify Request | 3 - PartModification |  | Low (2)
912 | 2-CPR-Attach file to Commercial Part Request as Modeler during Review stage | 2 - CommercialPartRequest |  | Low (2)
913 | 23-DocMgt-Rework Released Discontinuance Notices | 23 - DocumentManagement |  | Low (2)
914 | 27-Rep-Discrepancies found when running the ECN metrics | 27 - Reports (Teamcenter aka Query Builder) |  | Low (2)
915 | 5-CHG-Revising Migrated Parts with special revisions | 5 - ChangeECN |  | Low (2)
916 | 16-SR-Quick Search for Part Description | 16 - SearchAndReports |  | Low (2)
917 | 16-SR-Classification Part Family Alpha Sort | 16 - SearchAndReports |  | Low (2)
918 | 5-CHG-ECN Created without DSE forms | 5 - ChangeECN |  | Low (2)
919 | 1-PRT-Remove Description from Part Master | 1 - DivisionalPartRequest |  | Low (2)
920 | 14-SC-Supplier Transfer Utility fails to transfer parts when removed status on the AVL | 14 - SubstanceCompliance |  | Low (2)
921 | 30-TcRA-Add Item Status column in Part Qual report | 30 - TcRA Reports |  | Low (2)
For 746:
[7 empty] | This is the actual info of ECN031134 on Teamcenter |  |  |  | This is the screenshot on the Test case
VS
For 900:
Insufficient information on Test case about Doc1 and Doc2

## Summary
Total Test Cases for Regression | 385 | January 31 | 54
|  | February 28 | 82
|  | March 31 | 99
|  | April 30 | 85
|  | May 31 | 65
385